## SUMMARY
Project name : | PROPOSED THREE STORY RESIDENCE
Location : | GRAND CENTENIAL HOMES KAWIT CAVITE
Date : | 2026-08-17
|  | Total Area: | 387.9 | sq.m | [10 empty] | 3500 | water cs
ITEM NO | WORK ITEM DESCRIPTION | Total Amount Php | Cost per Sq.m | Weighted % age | AMOUNT | [5 empty] | PERCENTAGE ACCOMPLISHMENT |  |  | BALANCE AMOUNT | 2000 | shower
A | GENERAL REQUIREMENTS |  |  |  | THIS DATE | 1900000 |  |  |  |  | PREVIOUS | THIS DATE | TO DATE
| General Requirements Sub-total: | 599000 | 1544.2124 | 6.507% | 157250 | [5 empty] | 50% | 26.25% | 76.25% | 142250
B | ARCHITECTURAL WORKS
| Ceiling Finish | 942300.4381 | 2429.2355 | 10.24% | 134756.6273 | 78.45% | 21.55% |  | 1100379.8198 |  | 86.08% | 13.92% | 100% | 42.7347
| Floor Finish | 368899.08 | 951.0159 | 4.007% | 77840.0304 | [5 empty] | 84.25% | 9% | 93.25% | 24900.6879
| Wall Finish | 2040984.176 | 5261.6246 | 22.17% | 655611.8976 | 521974.5711 |  |  |  |  | 32.32% | 34.31% | 66.63% | 681105.5764
| Cabinet's | 2421974.5711 | 6243.8117 | 26.31% | 996590.4975 | [5 empty] | 12.03% | 36.21% | 48.24% | 1253685.8002
| Door's and Window's | 1561707.2 | 4026.0562 | 16.96% | 241863.6 | [5 empty] | 54.76% | 4.762% | 59.52% | 632119.581
| Architectural Sub-total: | 7335865.4652 | 18911.7439 | 79.69% | 2106662.6528 | 521975.3555 | 0.21552 | 0 | 1100379.8198 | 0 | 53.89% | 19.64% | 73.53% | 2591854.3802
C | PLUMBING WORKS
| Plumbing Fixtures | 56500 | 145.6561 | 0.6137% | 0 | [5 empty] | 0% | 0% | 0% | 56500
| Plumbing Sub-total: | 56500 | 145.6561 | 0.6137% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 56500
D | ELECTRICAL WORKS
| Lighting Fixtures | 607624 | 1566.445 | 6.601% | 121524.8 | [5 empty] | 0% | 20% | 20% | 486099.2
| Switches | 38841 | 100.1315 | 0.4219% | 14368.75 | [5 empty] | 0% | 36.67% | 36.67% | 24599.3
| Outlets | 66825 | 172.2738 | 0.7259% | 26730 | 7335865.4652 |  |  |  |  | 0% | 40% | 40% | 40095
| Wires | 375412.6761 | 967.8079 | 4.078% | 96533.4025 | [5 empty] | 69.75% | 21.25% | 91% | 33787.1408
| Panel Board | 125655.42 | 323.9377 | 1.365% | 13471.7 | [5 empty] | 0% | 8.333% | 8.333% | 115184.135
| Electrical Sub-total: | 1214358.0961 | 3130.5958 | 13.19% | 272628.6525 | 272628.6525 | 941729.4436 | 25.25% | 0 | 0 | 13.95% | 25.25% | 39.2% | 699764.7758
| Direct Sub-Total: | 9205723.5613 | 23732.2082 | 100% | 2536541.3053 | 794604.0081 | 941729.6591 | 0.2525 | 1100379.8198 | 0 | 29.46% | 17.79% | 47.24% | 3490369.1561
| Profit 7%: | 644400.6493 |  |  | 114608.6712 | [5 empty] | 29.46% | 17.79% | 47.24% | 339955.0714
| OCM 8%: | 736457.8849 |  |  | 130981.3385 |  |  |  | 1270389.8515 |  | 29.46% | 17.79% | 47.24% | 388520.0816
| Indirect Total Cost: | 10586582.0955 | 27292.0394 | 100% | 1882856.7404 | 794604.0081 | 941729.6591 | 0.2525 | 2370769.6712 | 0 | 29.46% | 17.79% | 47.24% | 4218844.3091
| DISCOUNTED AMOUNT: | 10300000 | 26553.2354 | 100% | 1831887.2183 | Overall Profit: |  | 2370769.6712 |  |  | 29.46% | 17.79% | 47.24% | 5433789.118
BILLING SUMMARY
| PREVIOUS | THIS DATE | TO DATE | [13 empty] | 3090000
CONTRACT AMOUNT | 3034323.6637 | 1831887.2183 | 4866210.882
DEDUCTIONS | [16 empty] | 4866210.882
RETENTION 5% | -151716.1832 | -91594.3609 | -243310.5441 | [13 empty] | 5433789.118
RECOUPMENT 30% | -910297.0991 | -549566.1655 | -1459863.2646
TOTAL BILLING THIS DATE | 1972310.3814 | 1190726.6919 | 3163037.0733
%AGE BILLING THIS DATE | 29.46% | 17.79% | 47.24%
Remaining To Bill
Billing no. 2 | 21759.23
Total : | 21759.23
BANK DETAILS:
BANK NAME: | Saiko Builders Construction Services
BPI ACCOUNT NUMBER: | 8930- 0154 -83
TOTAL AMOUNT: | 1212485.9219
Prepared By: |  |  |  |  | Approved By:
ENGR. Nadine D. Usman
QUANTITY SURVEYOR
ENGR. Kiel Caryl Buscayno
QUANTITY SURVEYOR
John Karl S. Quizon
QUANTITY SURVEYOR
Aljohn A. David
QUANTITY SURVEYOR
Reviewed By :
ENGR. John Mark Evangelista
VICE PRESIDENT-COO
Unit 6&7 E.M Razon Commercial Building, San Pedro Camuning,
Mexico, Pampanga, Philippines 2021
09951119535 | clients@saikobuilders.com

## BOQ
Project name : | PROPOSED THREE STORY RESIDENCE
Location : | GRAND CENTENIAL HOMES KAWIT CAVITE
Date : | 2026-08-17
[22 empty] | QUANTITY | [7 empty] | AMOUNT | [7 empty] | ACCOMPLISHMENT | PREVIOUS ACCOMPLISHMENT
ITEM NO | Description | QUANTITY | QUANTITY | UNIT | Material Cost Php/unit | Labor and Equipment Cost Php/unit | Total Cost Php/Unit | Total Amount Php |  |  |  |  | QUANTITY |  |  |  | AMOUNT |  |  |  | PERCENTAGE | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | BILLING 1 | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8
A | GENERAL REQUIREMENTS | [11 empty] | PREVIOUS | THIS DATE | TO DATE | BALANCE | PREVIOUS | THIS DATE | TO DATE | BALANCE | Accomplishment
| Mobilization/Demobilization | 1 | 1 | lot
| Site Management | 10 | 8 | month/s |  | 35000 | 35000 | 280000 |  |  |  |  | 2.4 | 2 | 4.4 | 3.6 | 0 | 70000 | 70000 | 210000 | 25% | 2.4 | [7 empty] | 84000 | [7 empty] | 25% | 30% | 20%
| Government Permits and Taxes | 1 |  | lot |  | by owner | by owner
| Services and Utilities | 10 | 8 | month/s |  | 8000 | 8000 | 64000 |  |  |  |  | 2.4 | 2 | 4.4 | 3.6 | 0 | 16000 | 16000 | 48000 | 25% | 2.4 | [7 empty] | 19200 | [7 empty] | 25% | 30% | 20%
| Temporary Facilities | 10 | 8 | month/s |  | 15000 | 15000 | 120000 |  |  |  |  | 2.4 | 2 | 4.4 | 3.6 | 19200 | 30000 | 49200 | 70800 | 25% | 2.4 | [7 empty] | 36000 | [7 empty] | 25% | 30% | 20%
| Engineering plans, Shop Drawings & Asbuilt | 1 | 1 | lot |  | - | DISCOUNTED
| Hauling and Disposal | 1 | 1 | lot |  | 60000 | 60000 | 60000 |  |  |  |  | 0.3 | 0.25 | 0.55 | 0.45 | 0 | 15000 | 15000 | 45000 | 25% | 0.3 | [7 empty] | 18000 | [7 empty] | 25% | 30% | 20%
| Housekeeping | 1 | 1 | lot |  |  | Included
| Safety | 1 | 1 | lot |  |  | Included
| Scaffolding | 1 | 1 | lot |  | 75000 | 75000 | 75000 |  |  |  |  | 0.3 | 0.35 | 0.65 | 0.35 | 0 | 26250 | 26250 | 48750 | 35% | 0.3 | [7 empty] | 22500 | [7 empty] | 35% | 30% | 20%
| General Requirements Sub-total: | [6 empty] | 599000 |  |  |  |  | 7.8 | 6.6 | 14.4 | 11.6 | 19200 | 157250 | 176450 | 422550 | 27% | 7.8 | [7 empty] | 179700 | [8 empty] | 30% | 20%
B | ARCHITECTURAL WORKS
Ceiling Finish
Ground Floor (Interior)
| HALLWAY, LIVING, DINING TO KITCHEN AREA | [9 empty] | 60.4
| Gypsum Board | 88.72 | 97.592 | sq.m | 250 | 350 | 600 | 58555.2 |  |  | 1.4689 |  | 48.796 | 9.7592 | 58.5552 | 39.0368 | 0 | 5855.52 | 5855.52 | 52699.68 | 10% | 48.796 | [7 empty] | 29277.6 | [7 empty] | 10% | 50% | 40%
| CARRYING channel | 66.0993 | 72.7093 | l.m | 126.5 | 70 | 196.5 | 14287.3719 |  |  |  | 85 | 36.3546 | 7.2709 | 43.6256 | 29.0837 | 29277.6 | 1428.7372 | 30706.3372 | -16418.9653 | 10% | 36.3546 | [7 empty] | 7143.6859 | [7 empty] | 10% | 50% | 40%
| Metal Furring | 124.8543 | 137.3397 | l.m | 126.5 | 70 | 196.5 | 26987.2579 | Multiplier Mark up |  |  | 30 | 68.6699 | 13.734 | 82.4038 | 54.9359 | 7143.6859 | 2698.7258 | 9842.4117 | 17144.8462 | 10% | 68.6699 | [7 empty] | 13493.629 | [7 empty] | 10% | 50% | 40%
| Hanger clips | 44.0662 | 49 | pcs | 30 | 20 | 50 | 2450 | 1.1 |  |  | 110 | 24.5 | 4.9 | 29.4 | 19.6 | 13493.629 | 245 | 13738.629 | -11288.629 | 10% | 24.5 | [7 empty] | 1225 | [7 empty] | 10% | 50% | 40%
| W clips | 161.5762 | 178 | pcs | 10 | 20 | 30 | 5340 |  |  |  | 46.32 | 89 | 17.8 | 106.8 | 71.2 | 1225 | 534 | 1759 | 3581 | 10% | 89 | [7 empty] | 2670 | [7 empty] | 10% | 50% | 40%
| Wall Angle | 68.0383 | 75 | l.m | 110 | 60 | 170 | 12750 |  |  |  |  | 37.5 | 7.5 | 45 | 30 | 2670 | 1275 | 3945 | 8805 | 10% | 37.5 | [7 empty] | 6375 | [7 empty] | 10% | 50% | 40%
Miscellaneous
POWDER ROOM
| Ficem Board | 4 | 4.4 | sq.m | 250 | 350 | 600 | 2640 | 0.05 |  |  |  | 1.32 | 1.276 | 2.596 | 1.804 | 0 | 765.6 | 765.6 | 1874.4 | 29% | 1.32 | [7 empty] | 792 | [7 empty] | 29% | 30% | 40%
| CARRYING channel | 3.3333 | 3.6667 | l.m | 126.5 | 70 | 196.5 | 720.5 |  |  |  |  | 1.1 | 1.0633 | 2.1633 | 1.5033 | 792 | 208.945 | 1000.945 | -280.445 | 29% | 1.1 | [7 empty] | 216.15 | [7 empty] | 29% | 30% | 40%
| Metal Furring | 6.6667 | 7.3333 | l.m | 126.5 | 70 | 196.5 | 1441 |  |  |  |  | 2.2 | 2.1267 | 4.3267 | 3.0067 | 216.15 | 417.89 | 634.04 | 806.96 | 29% | 2.2 | [7 empty] | 432.3 | [7 empty] | 29% | 30% | 40%
| Hanger clips | 4 | 5 | pcs | 30 | 20 | 50 | 250 |  |  |  |  | 1.5 | 1.45 | 2.95 | 2.05 | 432.3 | 72.5 | 504.8 | -254.8 | 29% | 1.5 | [7 empty] | 75 | [7 empty] | 29% | 30% | 40%
| W clips | 12 | 14 | pcs | 10 | 20 | 30 | 420 |  |  |  |  | 4.2 | 4.06 | 8.26 | 5.74 | 75 | 121.8 | 196.8 | 223.2 | 29% | 4.2 | [7 empty] | 126 | [7 empty] | 29% | 30% | 40%
| Wall Angle | 7 | 8 | l.m | 110 | 60 | 170 | 1360 |  |  |  |  | 2.4 | 2.32 | 4.72 | 3.28 | 126 | 394.4 | 520.4 | 839.6 | 29% | 2.4 | [7 empty] | 408 | [7 empty] | 29% | 30% | 40%
| Paint flat finish | 185.44 | 203.984 | sq.m | 250 | 350 | 600 | 122390.4 |  |  |  |  | 61.1952 | 59.1554 | 120.3506 | 83.6334 | 0 | 35493.216 | 35493.216 | 86897.184 | 29% | 61.1952 | [7 empty] | 36717.12 | [7 empty] | 29% | 30% | 40%
Ground Floor (Exterior)
| PVC ceiling Panel | 39 | 42.9 | sq.m | 250 | 350 | 600 | 25740 |  |  | 39 | 24.5 | 21.45 | 3.861 | 25.311 | 17.589 | 0 | 2316.6 | 2316.6 | 23423.4 | 9% | 21.45 | [7 empty] | 12870 | [7 empty] | 9% | 50% | 40%
| CARRYING channel | 44.7704 | 49.2474 | l.m | 126.5 | 70 | 196.5 | 9677.1237 |  |  | 1.5918 | 28.125 | 24.6237 | 4.4323 | 29.056 | 20.1915 | 12870 | 870.9411 | 13740.9411 | -4063.8174 | 9% | 24.6237 | [7 empty] | 4838.5619 | [7 empty] | 9% | 50% | 40%
| Metal Furring | 72.1367 | 79.3504 | l.m | 126.5 | 70 | 196.5 | 15592.3552 |  |  |  | 45.3167 | 39.6752 | 7.1415 | 46.8167 | 32.5337 | 4838.5619 | 1403.312 | 6241.8738 | 9350.4814 | 9% | 39.6752 | [7 empty] | 7796.1776 | [7 empty] | 9% | 50% | 40%
| Hanger clips | 14.3265 | 16 | pcs | 30 | 20 | 50 | 800 |  |  |  | 9 | 8 | 1.44 | 9.44 | 6.56 | 7796.1776 | 72 | 7868.1776 | -7068.1776 | 9% | 8 | [7 empty] | 400 | [7 empty] | 9% | 50% | 40%
| W clips | 216.4898 | 239 | pcs | 10 | 20 | 30 | 7170 |  |  |  | 136 | 119.5 | 21.51 | 141.01 | 97.99 | 400 | 645.3 | 1045.3 | 6124.7 | 9% | 119.5 | [7 empty] | 3585 | [7 empty] | 9% | 50% | 40%
| H CLIP | 2.0057 | 2.2063 | l.m | 110 | 20 | 130 | 286.8171 |  |  |  | 1.26 | 1.1031 | 0.19857 | 1.3017 | 0.90458 | 3585 | 25.8135 | 3610.8135 | -3323.9964 | 9% | 1.1031 | [7 empty] | 143.4086 | [7 empty] | 9% | 50% | 40%
| edging | 77.0449 | 84.7494 | l.m | 110 | 20 | 130 | 11017.4204 |  |  |  | 48.4 | 42.3747 | 7.6274 | 50.0021 | 34.7472 | 143.4086 | 991.5678 | 1134.9764 | 9882.444 | 9% | 42.3747 | [7 empty] | 5508.7102 | [7 empty] | 9% | 50% | 40%
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 15993.7723 |  |  |  |  | 0.5 | 0.1 | 0.6 | 0.4 | 0 | 1599.3772 | 1599.3772 | 14394.3951 | 10% | 0.5 | [7 empty] | 7996.8862 | [7 empty] | 10% | 50% | 40%
| Ground Floor Ceiling Sub-total: | [6 empty] | 335869.2186 |  |  |  |  | 635.9625 | 178.7263 | 814.6887 | 555.7898 | 85084.5129 | 57436.2457 | 142520.7586 | 193348.46 | 16% | 635.9625 | [7 empty] | 142090.2293 | [8 empty] | 43.33% | 40%
Second Floor (Interior)
BEDROOM 1
| Gypsum Board | 12.7 | 13.97 | sq.m | 250 | 350 | 600 | 8382 |  |  |  |  | 9.2202 | 0 | 9.2202 | 4.7498 | 0 | 0 | 0 | 8382 | 0% | 9.2202 | [7 empty] | 5532.12 | [7 empty] | 0% | 66% | 40%
| CARRYING channel | 10.53 | 11.583 | l.m | 126.5 | 70 | 196.5 | 2276.0595 |  |  |  |  | 7.6448 | 0 | 7.6448 | 3.9382 | 5532.12 | 0 | 5532.12 | -3256.0605 | 0% | 7.6448 | [7 empty] | 1502.1993 | [7 empty] | 0% | 66% | 40%
| Metal Furring | 21.06 | 23.166 | l.m | 126.5 | 70 | 196.5 | 4552.119 |  |  |  |  | 15.2896 | 0 | 15.2896 | 7.8764 | 1502.1993 | 0 | 1502.1993 | 3049.9197 | 0% | 15.2896 | [7 empty] | 3004.3985 | [7 empty] | 0% | 66% | 40%
| Hanger clips | 6 | 7 | pcs | 30 | 20 | 50 | 350 |  |  |  |  | 4.62 | 0 | 4.62 | 2.38 | 3004.3985 | 0 | 3004.3985 | -2654.3985 | 0% | 4.62 | [7 empty] | 231 | [7 empty] | 0% | 66% | 40%
| W clips | 28 | 31 | pcs | 10 | 20 | 30 | 930 |  |  |  |  | 20.46 | 0 | 20.46 | 10.54 | 231 | 0 | 231 | 699 | 0% | 20.46 | [7 empty] | 613.8 | [7 empty] | 0% | 66% | 40%
| Wall Angle | 14.2 | 16 | l.m | 110 | 60 | 170 | 2720 |  |  |  |  | 10.56 | 0 | 10.56 | 5.44 | 613.8 | 0 | 613.8 | 2106.2 | 0% | 10.56 | [7 empty] | 1795.2 | [7 empty] | 0% | 66% | 40%
| Paint flat finish | 25.4 | 27.94 | sq.m | 250 | 350 | 600 | 16764 |  |  |  |  | 18.4404 | 0 | 18.4404 | 9.4996 | 1795.2 | 0 | 1795.2 | 14968.8 | 0% | 18.4404 | [7 empty] | 11064.24 | [7 empty] | 0% | 66% | 40%
BEDROOM 2
| Gypsum Board | 14.8 | 16.28 | sq.m | 250 | 350 | 600 | 9768 |  |  |  |  | 8.14 | 1.628 | 9.768 | 6.512 | 0 | 976.8 | 976.8 | 8791.2 | 10% | 8.14 | [7 empty] | 4884 | [7 empty] | 10% | 50% | 40%
| CARRYING channel | 12.36 | 13.596 | l.m | 126.5 | 70 | 196.5 | 2671.614 |  |  |  |  | 6.798 | 1.3596 | 8.1576 | 5.4384 | 4884 | 267.1614 | 5151.1614 | -2479.5474 | 10% | 6.798 | [7 empty] | 1335.807 | [7 empty] | 10% | 50% | 40%
| Metal Furring | 24.72 | 27.192 | l.m | 126.5 | 70 | 196.5 | 5343.228 |  |  |  |  | 13.596 | 2.7192 | 16.3152 | 10.8768 | 1335.807 | 534.3228 | 1870.1298 | 3473.0982 | 10% | 13.596 | [7 empty] | 2671.614 | [7 empty] | 10% | 50% | 40%
| Hanger clips | 7 | 8 | pcs | 30 | 20 | 50 | 400 |  |  |  |  | 4 | 0.8 | 4.8 | 3.2 | 2671.614 | 40 | 2711.614 | -2311.614 | 10% | 4 | [7 empty] | 200 | [7 empty] | 10% | 50% | 40%
| W clips | 32 | 36 | pcs | 10 | 20 | 30 | 1080 |  |  |  |  | 18 | 3.6 | 21.6 | 14.4 | 200 | 108 | 308 | 772 | 10% | 18 | [7 empty] | 540 | [7 empty] | 10% | 50% | 40%
| Wall Angle | 15.2 | 17 | l.m | 110 | 60 | 170 | 2890 |  |  |  |  | 8.5 | 1.7 | 10.2 | 6.8 | 540 | 289 | 829 | 2061 | 10% | 8.5 | [7 empty] | 1445 | [7 empty] | 10% | 50% | 40%
| Ficem Board ( T&B ) | 3.8 | 4.18 | sq.m | 250 | 350 | 600 | 2508 |  |  |  |  | 2.09 | 0.836 | 2.926 | 1.254 | 0 | 501.6 | 501.6 | 2006.4 | 20% | 2.09 | [7 empty] | 1254 | [7 empty] | 20% | 50% | 30%
| CARRYING channel | 3.1995 | 3.5195 | l.m | 126.5 | 70 | 196.5 | 691.5719 |  |  |  |  | 1.7597 | 0.70389 | 2.4636 | 1.0558 | 1254 | 138.3144 | 1392.3144 | -700.7425 | 20% | 1.7597 | [7 empty] | 345.786 | [7 empty] | 20% | 50% | 30%
| Metal Furring | 6.399 | 7.0389 | l.m | 126.5 | 70 | 196.5 | 1383.1439 |  |  |  |  | 3.5195 | 1.4078 | 4.9272 | 2.1117 | 345.786 | 276.6288 | 622.4147 | 760.7291 | 20% | 3.5195 | [7 empty] | 691.5719 | [7 empty] | 20% | 50% | 30%
| Hanger clips | 5 | 6 | pcs | 30 | 20 | 50 | 300 |  |  |  |  | 3 | 1.2 | 4.2 | 1.8 | 691.5719 | 60 | 751.5719 | -451.5719 | 20% | 3 | [7 empty] | 150 | [7 empty] | 20% | 50% | 30%
| W clips | 12 | 14 | pcs | 10 | 20 | 30 | 420 |  |  |  |  | 7 | 2.8 | 9.8 | 4.2 | 150 | 84 | 234 | 186 | 20% | 7 | [7 empty] | 210 | [7 empty] | 20% | 50% | 30%
| Wall Angle | 8 | 9 | l.m | 110 | 60 | 170 | 1530 |  |  |  |  | 4.5 | 1.8 | 6.3 | 2.7 | 210 | 306 | 516 | 1014 | 20% | 4.5 | [7 empty] | 765 | [7 empty] | 20% | 50% | 30%
| Paint flat finish | 37.2 | 40.92 | sq.m | 250 | 350 | 600 | 24552 |  |  |  |  | 20.46 | 8.184 | 28.644 | 12.276 | 765 | 4910.4 | 5675.4 | 18876.6 | 20% | 20.46 | [7 empty] | 12276 | [7 empty] | 20% | 50% | 30%
BEDROOM 3
| Gypsum Board | 15.5 | 17.05 | sq.m | 250 | 350 | 600 | 10230 |  |  |  |  | 8.525 | 2.5575 | 11.0825 | 5.9675 | 0 | 1534.5 | 1534.5 | 8695.5 | 15% | 8.525 | [7 empty] | 5115 | [7 empty] | 15% | 50% | 35%
| CARRYING channel | 12.972 | 14.2692 | l.m | 126.5 | 70 | 196.5 | 2803.8978 |  |  |  |  | 7.1346 | 2.1404 | 9.275 | 4.9942 | 5115 | 420.5847 | 5535.5847 | -2731.6869 | 15% | 7.1346 | [7 empty] | 1401.9489 | [7 empty] | 15% | 50% | 35%
| Metal Furring | 25.944 | 28.5384 | l.m | 126.5 | 70 | 196.5 | 5607.7956 |  |  |  |  | 14.2692 | 4.2808 | 18.55 | 9.9884 | 1401.9489 | 841.1693 | 2243.1182 | 3364.6774 | 15% | 14.2692 | [7 empty] | 2803.8978 | [7 empty] | 15% | 50% | 35%
| Hanger clips | 7 | 8 | pcs | 30 | 20 | 50 | 400 |  |  |  |  | 4 | 1.2 | 5.2 | 2.8 | 2803.8978 | 60 | 2863.8978 | -2463.8978 | 15% | 4 | [7 empty] | 200 | [7 empty] | 15% | 50% | 35%
| W clips | 33 | 37 | pcs | 10 | 20 | 30 | 1110 |  |  |  |  | 18.5 | 5.55 | 24.05 | 12.95 | 200 | 166.5 | 366.5 | 743.5 | 15% | 18.5 | [7 empty] | 555 | [7 empty] | 15% | 50% | 35%
| Wall Angle | 15.8 | 18 | l.m | 110 | 60 | 170 | 3060 |  |  |  |  | 9 | 2.7 | 11.7 | 6.3 | 555 | 459 | 1014 | 2046 | 15% | 9 | [7 empty] | 1530 | [7 empty] | 15% | 50% | 35%
| Paint flat finish | 31 | 34.1 | sq.m | 250 | 350 | 600 | 20460 |  |  |  |  | 17.05 | 5.115 | 22.165 | 11.935 | 1530 | 3069 | 4599 | 15861 | 15% | 17.05 | [7 empty] | 10230 | [7 empty] | 15% | 50% | 35%
BEDROOM 4
| Gypsum Board | 14.1 | 15.51 | sq.m | 250 | 350 | 600 | 9306 |  |  |  |  | 7.755 | 1.551 | 9.306 | 6.204 | 0 | 930.6 | 930.6 | 8375.4 | 10% | 7.755 | [7 empty] | 4653 | [7 empty] | 10% | 50% | 40%
| CARRYING channel | 12.213 | 13.4343 | l.m | 126.5 | 70 | 196.5 | 2639.84 |  |  |  |  | 6.7172 | 1.3434 | 8.0606 | 5.3737 | 4653 | 263.984 | 4916.984 | -2277.144 | 10% | 6.7172 | [7 empty] | 1319.92 | [7 empty] | 10% | 50% | 40%
| Metal Furring | 24.426 | 26.8686 | l.m | 126.5 | 70 | 196.5 | 5279.6799 |  |  |  |  | 13.4343 | 2.6869 | 16.1212 | 10.7474 | 1319.92 | 527.968 | 1847.888 | 3431.7919 | 10% | 13.4343 | [7 empty] | 2639.84 | [7 empty] | 10% | 50% | 40%
| Hanger clips | 7 | 8 | pcs | 30 | 20 | 50 | 400 |  |  |  |  | 4 | 0.8 | 4.8 | 3.2 | 2639.84 | 40 | 2679.84 | -2279.84 | 10% | 4 | [7 empty] | 200 | [7 empty] | 10% | 50% | 40%
| W clips | 32 | 36 | pcs | 10 | 20 | 30 | 1080 |  |  |  |  | 18 | 3.6 | 21.6 | 14.4 | 200 | 108 | 308 | 772 | 10% | 18 | [7 empty] | 540 | [7 empty] | 10% | 50% | 40%
| Wall Angle | 15.36 | 17 | l.m | 110 | 60 | 170 | 2890 |  |  |  |  | 8.5 | 1.7 | 10.2 | 6.8 | 540 | 289 | 829 | 2061 | 10% | 8.5 | [7 empty] | 1445 | [7 empty] | 10% | 50% | 40%
| Paint flat finish | 28.2 | 31.02 | sq.m | 250 | 350 | 600 | 18612 |  |  |  |  | 15.51 | 3.102 | 18.612 | 12.408 | 1445 | 1861.2 | 3306.2 | 15305.8 | 10% | 15.51 | [7 empty] | 9306 | [7 empty] | 10% | 50% | 40%
HALLWAY
| Gypsum Board | 23 | 25.3 | sq.m | 250 | 350 | 600 | 15180 |  |  |  |  | 12.65 | 2.53 | 15.18 | 10.12 | 0 | 1518 | 1518 | 13662 | 10% | 12.65 | [7 empty] | 7590 | [7 empty] | 10% | 50% | 40%
| CARRYING channel | 15 | 16.5 | l.m | 126.5 | 70 | 196.5 | 3242.25 |  |  |  |  | 8.25 | 1.65 | 9.9 | 6.6 | 7590 | 324.225 | 7914.225 | -4671.975 | 10% | 8.25 | [7 empty] | 1621.125 | [7 empty] | 10% | 50% | 40%
| Metal Furring | 30 | 33 | l.m | 126.5 | 70 | 196.5 | 6484.5 |  |  |  |  | 16.5 | 3.3 | 19.8 | 13.2 | 1621.125 | 648.45 | 2269.575 | 4214.925 | 10% | 16.5 | [7 empty] | 3242.25 | [7 empty] | 10% | 50% | 40%
| Hanger clips | 25 | 28 | pcs | 30 | 20 | 50 | 1400 |  |  |  |  | 14 | 2.8 | 16.8 | 11.2 | 3242.25 | 140 | 3382.25 | -1982.25 | 10% | 14 | [7 empty] | 700 | [7 empty] | 10% | 50% | 40%
| W clips | 54 | 60 | pcs | 10 | 20 | 30 | 1800 |  |  |  |  | 30 | 6 | 36 | 24 | 700 | 180 | 880 | 920 | 10% | 30 | [7 empty] | 900 | [7 empty] | 10% | 50% | 40%
| Wall Angle | 35 | 39 | l.m | 110 | 60 | 170 | 6630 |  |  |  |  | 19.5 | 3.9 | 23.4 | 15.6 | 900 | 663 | 1563 | 5067 | 10% | 19.5 | [7 empty] | 3315 | [7 empty] | 10% | 50% | 40%
| Paint flat finish | 46 | 50.6 | sq.m | 250 | 350 | 600 | 30360 |  |  |  |  | 25.3 | 5.06 | 30.36 | 20.24 | 3315 | 3036 | 6351 | 24009 | 10% | 25.3 | [7 empty] | 15180 | [7 empty] | 10% | 50% | 40%
Second Floor (Exterior)
| PVC ceiling Panel | 24.5 | 26.95 | sq.m | 250 | 350 | 600 | 16170 |  |  |  |  | 10.78 | 0 | 10.78 | 16.17 | 0 | 0 | 0 | 16170 | 0% | 10.78 | [7 empty] | 6468 | [7 empty] | 0% | 40% | 60%
| CARRYING channel | 28.125 | 30.9375 | l.m | 126.5 | 70 | 196.5 | 6079.2188 |  |  |  |  | 12.375 | 0 | 12.375 | 18.5625 | 6468 | 0 | 6468 | -388.7812 | 0% | 12.375 | [7 empty] | 2431.6875 | [7 empty] | 0% | 40% | 60%
| Metal Furring | 45.3167 | 49.8483 | l.m | 126.5 | 70 | 196.5 | 9795.1975 |  |  |  |  | 19.9393 | 0 | 19.9393 | 29.909 | 2431.6875 | 0 | 2431.6875 | 7363.51 | 0% | 19.9393 | [7 empty] | 3918.079 | [7 empty] | 0% | 40% | 60%
| Hanger clips | 9 | 10 | pcs | 30 | 20 | 50 | 500 |  |  |  |  | 4 | 0 | 4 | 6 | 3918.079 | 0 | 3918.079 | -3418.079 | 0% | 4 | [7 empty] | 200 | [7 empty] | 0% | 40% | 60%
| W clips | 136 | 150 | pcs | 10 | 20 | 30 | 4500 |  |  |  |  | 60 | 0 | 60 | 90 | 200 | 0 | 200 | 4300 | 0% | 60 | [7 empty] | 1800 | [7 empty] | 0% | 40% | 60%
| H CLIP | 1.26 | 1.386 | l.m | 110 | 20 | 130 | 180.18 |  |  |  |  | 0.5544 | 0 | 0.5544 | 0.8316 | 1800 | 0 | 1800 | -1619.82 | 0% | 0.5544 | [7 empty] | 72.072 | [7 empty] | 0% | 40% | 60%
| edging | 48.4 | 53.24 | l.m | 110 | 20 | 130 | 6921.2 |  |  |  |  | 21.296 | 0 | 21.296 | 31.944 | 72.072 | 0 | 72.072 | 6849.128 | 0% | 21.296 | [7 empty] | 2768.48 | [7 empty] | 0% | 40% | 60%
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 14131.6748 |  |  |  |  | 0.2 | 0.4 | 0.6 | 0.4 | 0 | 5652.6699 | 5652.6699 | 8479.0049 | 40% | 0.2 | [7 empty] | 2826.335 | [7 empty] | 40% | 20% | 30%
| Second Floor Ceiling Sub-total: | [6 empty] | 296765.1706 |  |  |  |  | 595.3381 | 92.7054 | 688.0435 | 525.8942 | 80388.3168 | 31226.0783 | 111614.3951 | 185150.7755 | 9.898% | 595.3381 | [7 empty] | 145484.3718 | [8 empty] | 50.24% | 40.51%
Third Floor (Interior)
HALLWAY
| Gypsum Board | 27 | 29.7 | sq.m | 250 | 350 | 600 | 17820 |  |  |  |  | 11.88 | 5.94 | 17.82 | 11.88 | 0 | 3564 | 3564 | 14256 | 20% | 11.88 | [7 empty] | 7128 | [7 empty] | 20% | 40% | 40%
| CARRYING channel | 22.638 | 24.9018 | l.m | 126.5 | 70 | 196.5 | 4893.2058 |  | 15.7 | 1.72 |  | 9.9607 | 4.9804 | 14.9411 | 9.9607 | 7128 | 978.6412 | 8106.6412 | -3213.4354 | 20% | 9.9607 | [7 empty] | 1957.2823 | [7 empty] | 20% | 40% | 40%
| Metal Furring | 45.276 | 49.8036 | l.m | 126.5 | 70 | 196.5 | 9786.4115 |  | 1.7197 | 8.6 |  | 19.9214 | 9.9607 | 29.8822 | 19.9214 | 1957.2823 | 1957.2823 | 3914.5646 | 5871.8469 | 20% | 19.9214 | [7 empty] | 3914.5646 | [7 empty] | 20% | 40% | 40%
| Hanger clips | 12.0382 | 14 | pcs | 30 | 20 | 50 | 700 |  |  | 8.6 |  | 5.6 | 2.8 | 8.4 | 5.6 | 3914.5646 | 140 | 4054.5646 | -3354.5646 | 20% | 5.6 | [7 empty] | 280 | [7 empty] | 20% | 40% | 40%
| W clips | 58.4713 | 65 | pcs | 10 | 20 | 30 | 1950 |  | 13.1636 |  |  | 26 | 13 | 39 | 26 | 280 | 390 | 670 | 1280 | 20% | 26 | [7 empty] | 780 | [7 empty] | 20% | 40% | 40%
| Wall Angle | 37.6624 | 42 | l.m | 110 | 60 | 170 | 7140 |  | 26.3272 |  |  | 16.8 | 8.4 | 25.2 | 16.8 | 780 | 1428 | 2208 | 4932 | 20% | 16.8 | [7 empty] | 2856 | [7 empty] | 20% | 40% | 40%
| Paint flat finish | 54 | 59.4 | sq.m | 250 | 350 | 600 | 35640 |  | 7 |  |  | 23.76 | 11.88 | 35.64 | 23.76 | 2856 | 7128 | 9984 | 25656 | 20% | 23.76 | [7 empty] | 14256 | [7 empty] | 20% | 40% | 40%
34
| MASTER'S BEDROOM TO WALK IN CLOSET | [8 empty] | 21.9
| Gypsum Board | 30 | 33 | sq.m | 250 | 350 | 600 | 19800 |  |  |  |  | 13.2 | 6.6 | 19.8 | 13.2 | 0 | 3960 | 3960 | 15840 | 20% | 13.2 | [7 empty] | 7920 | [7 empty] | 20% | 40% | 40%
| CARRYING channel | 25.6095 | 28.1704 | l.m | 126.5 | 70 | 196.5 | 5535.4934 |  |  |  |  | 11.2682 | 5.6341 | 16.9023 | 11.2682 | 7920 | 1107.0987 | 9027.0987 | -3491.6053 | 20% | 11.2682 | [7 empty] | 2214.1974 | [7 empty] | 20% | 40% | 40%
| Metal Furring | 51.219 | 56.3409 | l.m | 126.5 | 70 | 196.5 | 11070.9868 |  |  |  |  | 22.5364 | 11.2682 | 33.8045 | 22.5364 | 2214.1974 | 2214.1974 | 4428.3947 | 6642.5921 | 20% | 22.5364 | [7 empty] | 4428.3947 | [7 empty] | 20% | 40% | 40%
| Hanger clips | 16 | 18 | pcs | 30 | 20 | 50 | 900 |  |  |  |  | 7.2 | 3.6 | 10.8 | 7.2 | 4428.3947 | 180 | 4608.3947 | -3708.3947 | 20% | 7.2 | [7 empty] | 360 | [7 empty] | 20% | 40% | 40%
| W clips | 66 | 73 | pcs | 10 | 20 | 30 | 2190 |  |  |  |  | 29.2 | 14.6 | 43.8 | 29.2 | 360 | 438 | 798 | 1392 | 20% | 29.2 | [7 empty] | 876 | [7 empty] | 20% | 40% | 40%
| Wall Angle | 39.8 | 44 | l.m | 110 | 60 | 170 | 7480 |  |  |  |  | 17.6 | 8.8 | 26.4 | 17.6 | 876 | 1496 | 2372 | 5108 | 20% | 17.6 | [7 empty] | 2992 | [7 empty] | 20% | 40% | 40%
| Paint flat finish | 60 | 66 | sq.m | 250 | 350 | 600 | 39600 |  |  |  |  | 26.4 | 13.2 | 39.6 | 26.4 | 2992 | 7920 | 10912 | 28688 | 20% | 26.4 | [7 empty] | 15840 | [7 empty] | 20% | 40% | 40%
MASTER'S T & B
| Ficem Board | 12.9 | 14.19 | sq.m | 250 | 350 | 600 | 8514 |  |  |  |  | 5.676 | 2.838 | 8.514 | 5.676 | 0 | 1702.8 | 1702.8 | 6811.2 | 20% | 5.676 | [7 empty] | 3405.6 | [7 empty] | 20% | 40% | 40%
| CARRYING channel | 10.5658 | 11.6224 | l.m | 126.5 | 70 | 196.5 | 2283.8049 |  |  |  |  | 4.649 | 2.3245 | 6.9735 | 4.649 | 3405.6 | 456.761 | 3862.361 | -1578.5561 | 20% | 4.649 | [7 empty] | 913.522 | [7 empty] | 20% | 40% | 40%
| Metal Furring | 21.1317 | 23.2448 | l.m | 126.5 | 70 | 196.5 | 4567.6098 |  |  |  |  | 9.2979 | 4.649 | 13.9469 | 9.2979 | 913.522 | 913.522 | 1827.0439 | 2740.5658 | 20% | 9.2979 | [7 empty] | 1827.0439 | [7 empty] | 20% | 40% | 40%
| Hanger clips | 7 | 8 | pcs | 30 | 20 | 50 | 400 |  |  |  |  | 3.2 | 1.6 | 4.8 | 3.2 | 1827.0439 | 80 | 1907.0439 | -1507.0439 | 20% | 3.2 | [7 empty] | 160 | [7 empty] | 20% | 40% | 40%
| W clips | 29 | 32 | pcs | 10 | 20 | 30 | 960 |  |  |  |  | 12.8 | 6.4 | 19.2 | 12.8 | 160 | 192 | 352 | 608 | 20% | 12.8 | [7 empty] | 384 | [7 empty] | 20% | 40% | 40%
| Wall Angle | 14.5 | 16 | l.m | 110 | 60 | 170 | 2720 |  |  |  |  | 6.4 | 3.2 | 9.6 | 6.4 | 384 | 544 | 928 | 1792 | 20% | 6.4 | [7 empty] | 1088 | [7 empty] | 20% | 40% | 40%
| Paint flat finish | 25.8 | 28.38 | sq.m | 250 | 350 | 600 | 17028 |  |  |  |  | 11.352 | 5.676 | 17.028 | 11.352 | 1088 | 3405.6 | 4493.6 | 12534.4 | 20% | 11.352 | [7 empty] | 6811.2 | [7 empty] | 20% | 40% | 40%
Third Floor (Exterior)
| PVC ceiling Panel | 46.8 | 51.48 | sq.m | 250 | 350 | 600 | 30888 |  |  |  |  | 20.592 | 0 | 20.592 | 30.888 | 0 | 0 | 0 | 30888 | 0% | 20.592 | [7 empty] | 12355.2 | [7 empty] | 0% | 40% | 60%
| CARRYING channel | 76.0963 | 83.706 | l.m | 126.5 | 70 | 196.5 | 16448.2225 |  |  |  |  | 33.4824 | 0 | 33.4824 | 50.2236 | 12355.2 | 0 | 12355.2 | 4093.0224 | 0% | 33.4824 | [7 empty] | 6579.289 | [7 empty] | 0% | 40% | 60%
| Metal Furring | 114.1445 | 125.559 | l.m | 126.5 | 70 | 196.5 | 24672.3337 |  |  |  |  | 50.2236 | 0 | 50.2236 | 75.3354 | 6579.289 | 0 | 6579.289 | 18093.0447 | 0% | 50.2236 | [7 empty] | 9868.9335 | [7 empty] | 0% | 40% | 60%
| Hanger clips | 46 | 51 | pcs | 30 | 20 | 50 | 2550 |  |  |  |  | 20.4 | 0 | 20.4 | 30.6 | 9868.9335 | 0 | 9868.9335 | -7318.9335 | 0% | 20.4 | [7 empty] | 1020 | [7 empty] | 0% | 40% | 60%
| W clips | 274 | 302 | pcs | 10 | 20 | 30 | 9060 |  |  |  |  | 120.8 | 0 | 120.8 | 181.2 | 1020 | 0 | 1020 | 8040 | 0% | 120.8 | [7 empty] | 3624 | [7 empty] | 0% | 40% | 60%
| H CLIP | 7.1817 | 7.8998 | l.m | 110 | 20 | 130 | 1026.9783 |  |  |  |  | 3.1599 | 0 | 3.1599 | 4.7399 | 3624 | 0 | 3624 | -2597.0217 | 0% | 3.1599 | [7 empty] | 410.7913 | [7 empty] | 0% | 40% | 60%
| edging | 65 | 71.5 | l.m | 110 | 20 | 130 | 9295 |  |  |  |  | 28.6 | 0 | 28.6 | 42.9 | 410.7913 | 0 | 410.7913 | 8884.2087 | 0% | 28.6 | [7 empty] | 3718 | [7 empty] | 0% | 40% | 60%
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 14746.0023 |  |  |  |  | 0.3 | 0.4 | 0.7 | 0.3 | 0 | 5898.4009 | 5898.4009 | 8847.6014 | 40% | 0.3 | [7 empty] | 4423.8007 | [7 empty] | 40% | 30% | 30%
| Third Floor Ceiling Sub-total: | [6 empty] | 309666.049 |  |  |  |  | 572.2595 | 147.7508 | 720.0103 | 710.8885 | 77342.8187 | 46094.3034 | 123437.122 | 186228.927 | 15.86% | 572.2595 | [7 empty] | 122391.8194 | [8 empty] | 39.66% | 44.48%
| Ceiling Finish Sub-total: | [6 empty] | 942300.4381 |  |  |  |  | 1803.5601 | 419.1825 | 2222.7426 | 1792.5724 | 242815.6484 | 134756.6273 | 377572.2758 | 564728.1624 | 13.92% | 1803.5601 | [7 empty] | 409966.4204 | [8 empty] | 44.41% | 41.66%
Floor Finish (Interior)
Ground Floor
| HALLWAY, LIVING, DINING TO KITCHEN AREA | [7 empty] | MULTIPLIER FLOOR FINSIH
| WHITE 600X600 mm MARBLE TILES HIGH GLOSS FINISH | 52.2 | 57.42 | sq.m | 1320 | 350 | 1670 | 95891.4 | 1.1 |  |  |  | 0 | 28.71 | 28.71 | 28.71 | 0 | 47945.7 | 47945.7 | 47945.7 | 50% | 0 | [7 empty] | 0 | [7 empty] | 50% |  | 50%
Office room
| WHITE 600X600 mm MARBLE TILES HIGH GLOSS FINISH | 4 | 4.4 | sq.m | 1320 | 350 | 1670 | 7348 | Miscellaneous |  |  |  | 0 | 2.2 | 2.2 | 2.2 | 0 | 3674 | 3674 | 3674 | 50% | 0 | [7 empty] | 0 | [7 empty] | 50% |  | 50%
| Powder room | [7 empty] | 0.2
| 300X300 mm WHITE MARBLE TILES NON SKID | 2.8 | 3.08 | sq.m | 880 | 350 | 1230 | 3788.4 |  |  |  |  | 0 | 0.924 | 0.924 | 2.156 | 0 | 1136.52 | 1136.52 | 2651.88 | 30% | 0 | [7 empty] | 0 | [7 empty] | 30% |  | 30%
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 21405.56 |  |  |  |  | 0.43 | 0.14 | 0.57 | 0.43 | 0 | 2996.7784 | 2996.7784 | 18408.7816 | 14% | 0.43 | [7 empty] | 9204.3908 | [7 empty] | 14% | 43% | 43%
| Ground Floor Flooring Sub-total: | [6 empty] | 128433.36 |  |  |  |  | 0.43 | 31.974 | 32.404 | 33.496 | 0 | 55752.9984 | 55752.9984 | 72680.3616 | 36% | 0.43 | [7 empty] | 9204.3908 | [8 empty] | 10.75% | 43.25%
Second Floor
Hallway
| SPC WOOD | 13.6 | 14.96 | sq.m | 300 | 350 | 650 | 9724 |  |  |  |  | 0 | 0 | 0 | 14.96 | 0 | 0 | 0 | 9724 | 0% | 0 | [7 empty] | 0
Bedroom 1
| SPC WOOD | 11.5 | 12.65 | sq.m | 300 | 350 | 650 | 8222.5 |  |  |  |  | 0 | 0 | 0 | 12.65 | 0 | 0 | 0 | 8222.5 | 0% | 0 | [7 empty] | 0
Bedrorm 2
| SPC WOOD | 13.4 | 14.74 | sq.m | 300 | 350 | 650 | 9581 |  |  |  |  | 0 | 0 | 0 | 14.74 | 0 | 0 | 0 | 9581 | 0% | 0 | [7 empty] | 0
Bedroom 3
| SPC WOOD | 13.7 | 15.07 | sq.m | 300 | 350 | 650 | 9795.5 |  |  |  |  | 0 | 0 | 0 | 15.07 | 0 | 0 | 0 | 9795.5 | 0% | 0 | [7 empty] | 0
Bedroom 4
| SPC WOOD | 12.8 | 14.08 | sq.m | 300 | 350 | 650 | 9152 |  |  |  |  | 0 | 0 | 0 | 14.08 | 0 | 0 | 0 | 9152 | 0% | 0 | [7 empty] | 0
Toilet and Bath bedrrom 2
| 300X300 mm LIGHT GRAY TILES MARBLE LOOK IN NON- SKID FINISH | 3 | 3.3 | sq.m | 880 | 350 | 1230 | 4059 |  |  |  |  | 0 | 1.32 | 1.32 | 1.98 | 0 | 1623.6 | 1623.6 | 2435.4 | 40% | 0 | [7 empty] | 0 | [7 empty] | 40% |  | 40%
Toilet and Bath bedrrom
| 600x600mm White Tiles In Marble Look Non Skid | 6 | 6.6 | sq.m | 940 | 350 | 1290 | 8514 |  |  |  |  | 0 | 2.64 | 2.64 | 3.96 | 0 | 3405.6 | 3405.6 | 5108.4 | 40% | 0 | [7 empty] | 0 | [7 empty] | 40% |  | 40%
Balcony
| 600x600mm Non Skid Gray Tiles | 19.1 | 21.01 | sq.m | 830 | 350 | 1180 | 24791.8 |  |  |  |  | 0 | 10.505 | 10.505 | 10.505 | 0 | 12395.9 | 12395.9 | 12395.9 | 50% | 0 | [7 empty] | 0 | [7 empty] | 50% |  | 50%
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 16767.96 |  |  |  |  | 0.43 | 0 | 0.43 | 0.57 | 0 | 0 | 0 | 16767.96 | 0% | 0.43 | [7 empty] | 7210.2228 | [7 empty] | 0% | 43% | 43%
| Second Floor Flooring Sub-total: | [6 empty] | 100607.76 |  |  |  |  | 0.43 | 14.465 | 14.895 | 88.515 | 0 | 17425.1 | 17425.1 | 83182.66 | 14.44% | 0.43 | [7 empty] | 7210.2228 | [8 empty] | 4.778% | 19.22% | 0%
Third Floor
Hallway
| SPC WOOD | 7.5 | 8.25 | sq.m | 300 | 350 | 650 | 5362.5 |  |  |  |  | 0 | 0 | 0 | 8.25 | 0 | 0 | 0 | 5362.5 | 0% | 0 | [7 empty] | 0
Walk in Closet
| SPC WOOD | 12.4 | 13.64 | sq.m | 300 | 350 | 650 | 8866 |  |  |  |  | 0 | 0 | 0 | 13.64 | 0 | 0 | 0 | 8866 | 0% | 0 | [7 empty] | 0
Master's Bedroom
| SPC WOOD | 17.5 | 19.25 | sq.m | 300 | 350 | 650 | 12512.5 |  |  |  |  | 0 | 0 | 0 | 19.25 | 0 | 0 | 0 | 12512.5 | 0% | 0 | [7 empty] | 0
Master's T&B
| 300X600mm Gray Marble Tiles in Non Skid Finish | 9.4 | 10.34 | sq.m | 950 | 350 | 1300 | 13442 |  |  |  |  | 0 | 0 | 0 | 10.34 | 0 | 0 | 0 | 13442 | 0% | 0 | [7 empty] | 0
Memorabilia
| 300x300mm Light Gray Marbles Tiles | 5.5 | 6.05 | sq.m | 880 | 350 | 1230 | 7441.5 |  |  |  |  | 0 | 0 | 0 | 6.05 | 0 | 0 | 0 | 7441.5 | 0% | 0 | [7 empty] | 0
Viewdeck
| 600x600mm Non Skid Gray Tiles | 23.6 | 25.96 | sq.m | 830 | 350 | 1180 | 30632.8 |  |  |  |  | 0 | 0 | 0 | 25.96 | 0 | 0 | 0 | 30632.8 | 0% | 0 | [7 empty] | 0
Balcony
| 600x600mm Non Skid Gray Tiles | 29.5 | 32.45 | sq.m | 830 | 350 | 1180 | 38291 |  |  |  |  | 0 | 0 | 0 | 32.45 | 0 | 0 | 0 | 38291 | 0% | 0 | [7 empty] | 0
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 23309.66 |  |  |  |  | 0.25 | 0.2 | 0.45 | 0.55 | 0 | 4661.932 | 4661.932 | 18647.728 | 20% | 0.25 | [7 empty] | 5827.415 | [7 empty] | 20% | 25% | 25%
| Third Floor Flooring Sub-total: | [6 empty] | 139857.96 |  |  |  |  | 0.25 | 0.2 | 0.45 | 116.49 | 0 | 4661.932 | 4661.932 | 135196.028 | 2.5% | 0.25 | [7 empty] | 5827.415 | [8 empty] | 3.125% | 3.125%
| Flooring Finish Sub-total: | [6 empty] | 368899.08 |  |  |  |  | 1.11 | 46.639 | 47.749 | 238.501 | 0 | 77840.0304 | 77840.0304 | 291059.0496 | 52.94% | 1.11 | [7 empty] | 22242.0286 | [8 empty] | 18.65% | 65.6%
Unit 6&7 E.M Razon Commercial Building, San Pedro Camuning,
Mexico, Pampanga, Philippines 2021
09951119535 | clients@saikobuilders.com

## wall
Unit 6&7 E.M Razon Commercial Building, San Pedro Camuning,
Mexico, Pampanga, Philippines 2021
09951119535 ¦ clients@saikobuilders.com
Project name : | PROPOSED THREE STORY RESIDENCE
Location : | GRAND CENTENIAL HOMES KAWIT CAVITE
Date : | 2026-08-17
[19 empty] | QUANTITY | [7 empty] | AMOUNT | [7 empty] | ACCOMPLISHMENT | [7 empty] | PREVIOUS ACCOMPLISHMENT
ITEM NO | Description | QUANTITY | QUANTITY | UNIT | Material Cost Php/unit | Labor and Equipment Cost Php/unit | Total Cost Php/Unit | Total Amount Php |  | QUANTITY |  |  |  | AMOUNT |  |  |  | PERCENTAGE | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8
| Wall Finish | [7 empty] | MARK UP | PREVIOUS | THIS DATE | TO DATE | BALANCE | PREVIOUS | THIS DATE | TO DATE | BALANCE | Accomplishment
| Ground Floor ( Interior ) | [7 empty] | 1.1
| FOYER, LIVING, DINING AND KITCHEN | [7 empty] | MISS
| White Mouldings | 20.3 | 22.33 | l.m | 550 | 350 | 900 | 20097 | 0.1 | 4.466 | 6.699 | 11.165 | 11.165 | 4019.4 | 6029.1 | 10048.5 | 10048.5 | 30% | 4.466 | [7 empty] | 4019.4 | [7 empty] | 30% | [7 empty] | 20% | 20%
| Hidden Door PU Stone Finish Light Beige | 5.8 | 6.38 | sqm | 2150 | 1200 | 3350 | 21373 |  | 1.276 | 1.914 | 3.19 | 3.19 | 4274.6 | 6411.9 | 10686.5 | 10686.5 | 30% | 1.276 | [7 empty] | 4274.6 | [7 empty] | 30% | [7 empty] | 20% | 20%
| White Fluted | 5.2 | 5.72 | sqm | 880 | 350 | 1230 | 7035.6 |  | 1.144 | 1.716 | 2.86 | 2.86 | 1407.12 | 2110.68 | 3517.8 | 3517.8 | 30% | 1.144 | [7 empty] | 1407.12 | [7 empty] | 30% | [7 empty] | 20% | 20%
| Laminated Synthetic Marble Finish | 7.4 | 8.14 | sqm | 3300 | 1650 | 4950 | 40293 |  | 1.628 | 2.442 | 4.07 | 4.07 | 8058.6 | 12087.9 | 20146.5 | 20146.5 | 30% | 1.628 | [7 empty] | 8058.6 | [7 empty] | 30% | [7 empty] | 20% | 20%
| Back Splash Quartz/ White Sintered Stone Terazzo look Finish | 1.1 | 1.21 | sqm | 6600 | 3300 | 9900 | 11979 |  | 0.242 | 0.363 | 0.605 | 0.605 | 2395.8 | 3593.7 | 5989.5 | 5989.5 | 30% | 0.242 | [7 empty] | 2395.8 | [7 empty] | 30% | [7 empty] | 20% | 20%
| Semi Gloss | 42.3 | 46.53 | sqm | 350 | 350 | 700 | 32571 |  | 9.306 | 13.959 | 23.265 | 23.265 | 6514.2 | 9771.3 | 16285.5 | 16285.5 | 30% | 9.306 | [7 empty] | 6514.2 | [7 empty] | 30% | [7 empty] | 20% | 20%
| Wood Laminated Finish | 1.6 | 1.76 | sqm | 825 | 350 | 1175 | 2068 |  | 0.352 | 0.528 | 0.88 | 0.88 | 413.6 | 620.4 | 1034 | 1034 | 30% | 0.352 | [7 empty] | 413.6 | [7 empty] | 30% | [7 empty] | 20% | 20%
| Beveled Clear Mirror 10mm THK | 2.5 | 2.75 | sqm | 1375 | 700 | 2075 | 5706.25 |  | 0.55 | 0.825 | 1.375 | 1.375 | 1141.25 | 1711.875 | 2853.125 | 2853.125 | 30% | 0.55 | [7 empty] | 1141.25 | [7 empty] | 30% | [7 empty] | 20% | 20%
| OFFICE |  |  |  | 0
| Biege Textured Wallpaper Finish | 15 | 16.5 | sqm | 825 | 350 | 1175 | 19387.5 |  | 1.65 | 4.95 | 6.6 | 9.9 | 1938.75 | 5816.25 | 7755 | 11632.5 | 30% | 1.65 | [7 empty] | 1938.75 | [7 empty] | 30% | [7 empty] | 10% | 10%
| PU Stone Textured Light Biege Finish | 3.8 | 4.18 | sqm | 2150 | 1200 | 3350 | 14003 |  | 0.418 | 1.254 | 1.672 | 2.508 | 1400.3 | 4200.9 | 5601.2 | 8401.8 | 30% | 0.418 | [7 empty] | 1400.3 | [7 empty] | 30% | [7 empty] | 10% | 10%
| 18 mm THK MDF Plywood Wall Cladding in Wood Finish w/ warm strip light | 3.7 | 4.07 | sqm | 1375 | 700 | 2075 | 8445.25 |  | 0.407 | 1.221 | 1.628 | 2.442 | 844.525 | 2533.575 | 3378.1 | 5067.15 | 30% | 0.407 | [7 empty] | 844.525 | [7 empty] | 30% | [7 empty] | 10% | 10%
| Semi Gloss Off White | 7.1 | 7.81 | sqm | 350 | 350 | 700 | 5467 |  | 0.781 | 2.343 | 3.124 | 4.686 | 546.7 | 1640.1 | 2186.8 | 3280.2 | 30% | 0.781 | [7 empty] | 546.7 | [7 empty] | 30% | [7 empty] | 10% | 10%
POWDER ROOM
| 60X120 Gray Marble Tiles In High Gloss Finish | 22 | 24.2 | sqm | 550 | 350 | 900 | 21780 |  | 2.42 | 14.52 | 16.94 | 7.26 | 2178 | 13068 | 15246 | 6534 | 60% | 2.42 | [7 empty] | 2178 | [7 empty] | 60% | [7 empty] | 10% | 10%
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 21020.56 |  | 0.1 | 0.6 | 0.7 | 0.3 | 2102.056 | 12612.336 | 14714.392 | 6306.168 | 60% | 0.1 | [7 empty] | 2102.056 | [7 empty] | 60% | [7 empty] | 10% | 10%
| Sub-Total for Ground Floor (Interior) | [6 empty] | 231226.16 |  | 24.74 | 53.334 | 78.074 | 74.506 | 37234.901 | 82208.016 | 119442.917 | 111783.243 | 34.29% | 24.74 | [7 empty] | 37234.901 | [15 empty] | 15.71% | 15.71%
Ground Floor ( Exterior )
| Exposed Aggregate Concrete Cladding | 1.6 | 1.76 | sqm | 350 | 350 | 700 | 1232 |  | 0.176 | 0.176 | 0.352 | 1.408 | 123.2 | 123.2 | 246.4 | 985.6 | 10% | 0.176 | [7 empty] | 123.2 | [7 empty] | 10% | [7 empty] | 10% | 10%
| Wall Flashing ( Dark Gray ) | 46.4 | 51.04 | Im | 550 | 350 | 900 | 45936 |  | 5.104 | 28.072 | 33.176 | 17.864 | 4593.6 | 25264.8 | 29858.4 | 16077.6 | 55% | 5.104 | [7 empty] | 4593.6 | [7 empty] | 55% | [7 empty] | 10% | 10%
| Wall Piaint Finish ( Off White ) | 69.82 | 76.802 | sqm | 350 | 350 | 700 | 53761.4 |  | 7.6802 | 46.0812 | 53.7614 | 23.0406 | 5376.14 | 32256.84 | 37632.98 | 16128.42 | 60% | 7.6802 | [7 empty] | 5376.14 | [7 empty] | 60% | [7 empty] | 10% | 10%
| Natural Limestone Tiles Texture Running Ashlar Pattern | 14.8 | 16.28 | sqm | 950 | 350 | 1300 | 21164 |  | 1.628 | 6.512 | 8.14 | 8.14 | 2116.4 | 8465.6 | 10582 | 10582 | 40% | 1.628 | [7 empty] | 2116.4 | [7 empty] | 40% | [7 empty] | 10% | 30%
| Wall Piaint Finish ( Dark Gray ) | 19.1 | 21.01 | sqm | 350 | 350 | 700 | 14707 |  | 2.101 | 12.606 | 14.707 | 6.303 | 1470.7 | 8824.2 | 10294.9 | 4412.1 | 60% | 2.101 | [7 empty] | 1470.7 | [7 empty] | 60% | [7 empty] | 10% | 10%
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 13680.04 |  | 0.1 | 0.5 | 0.6 | 0.4 | 1368.004 | 6840.02 | 8208.024 | 5472.016 | 50% | 0.1 | [7 empty] | 1368.004 | [7 empty] | 50% | [7 empty] | 10% | 15%
| Sub-total for Ground Floor (Exterior) | [6 empty] | 150480.44 |  | 16.7892 | 93.9472 | 110.7364 | 57.1556 | 15048.044 | 81774.66 | 96822.704 | 53657.736 | 45.83% | 16.7892 | [7 empty] | 15048.044 | [15 empty] | 10% | 14.17%
Second Floor ( Interior )
BEDROOM 1
| Wall in Light Biege Semi-Gloss Painted Finish | 39 | 42.9 | sqm | 350 | 350 | 700 | 30030 |  | 4.29 | 17.16 | 21.45 | 21.45 | 3003 | 12012 | 15015 | 15015 | 40% | 4.29 | [7 empty] | 3003 | [7 empty] | 40% | [7 empty] | 10% | 20%
| Wall in Light Biege Semi-Gloss Painted Finish with mouldings | 22.6 | 24.86 | Im | 550 | 350 | 900 | 22374 |  | 2.486 | 9.944 | 12.43 | 12.43 | 2237.4 | 8949.6 | 11187 | 11187 | 40% | 2.486 | [7 empty] | 2237.4 | [7 empty] | 40% | [7 empty] | 10% | 20%
| BEDROOM 2 (Room and T&B) |  |  |  | 0 | 0
| Wall in off Light semi gloss Painted Finish | 28 | 30.8 | sqm | 350 | 350 | 700 | 21560 |  | 3.08 | 15.4 | 18.48 | 12.32 | 2156 | 10780 | 12936 | 8624 | 50% | 3.08 | [7 empty] | 2156 | [7 empty] | 50% | [7 empty] | 10% | 10%
| Wall in Wood in Fluted Panel | 3.5 | 3.85 | sqm | 1100 | 330 | 1430 | 5505.5 |  | 0.385 | 1.54 | 1.925 | 1.925 | 550.55 | 2202.2 | 2752.75 | 2752.75 | 40% | 0.385 | [7 empty] | 550.55 | [7 empty] | 40% | [7 empty] | 10% | 10%
| Headboard in light brown leatherette | 6.2 | 6.82 | sqm | 350 | 350 | 700 | 4774 |  | 0.682 | 1.705 | 2.387 | 4.433 | 477.4 | 1193.5 | 1670.9 | 3103.1 | 25% | 0.682 | [7 empty] | 477.4 | [7 empty] | 25% | [7 empty] | 10% | 10%
| 60x120 Gray Tiles Marble look in High Gloss Finish | 22.81 | 25.091 | sqm | 950 | 350 | 1300 | 32618.3 |  | 2.5091 | 12.5455 | 15.0546 | 10.0364 | 3261.83 | 16309.15 | 19570.98 | 13047.32 | 50% | 2.5091 | [7 empty] | 3261.83 | [7 empty] | 50% | [7 empty] | 10% | 30%
| Mosaic Tiles Light Green Finish | 2.8 | 3.08 | sqm | 770 | 350 | 1120 | 3449.6 |  | 0.308 | 1.848 | 2.156 | 0.924 | 344.96 | 2069.76 | 2414.72 | 1034.88 | 60% | 0.308 | [7 empty] | 344.96 | [7 empty] | 60% | [7 empty] | 10% | 10%
| Clear Mirror With Warm Light | 3 | 3.3 | sqm | 1450 | 350 | 1800 | 5940 |  | 0.33 | 0.33 | 0.66 | 2.64 | 594 | 594 | 1188 | 4752 | 10% | 0.33 | [7 empty] | 594 | [7 empty] | 10% | [7 empty] | 10% | 10%
| BEDROOM 3 |  |  |  | 0 | 0
| Wall off White in Semi Gloss Painted Finish | 37.5 | 41.25 | sqm | 350 | 350 | 700 | 28875 |  | 4.125 | 12.375 | 16.5 | 24.75 | 2887.5 | 8662.5 | 11550 | 17325 | 30% | 4.125 | [7 empty] | 2887.5 | [7 empty] | 30% | [7 empty] | 10% | 10%
| Wall Cladding in Fluted white Painted Finish | 4.2 | 4.62 | sqm | 880 | 330 | 1210 | 5590.2 |  | 0.462 | 0.462 | 0.924 | 3.696 | 559.02 | 559.02 | 1118.04 | 4472.16 | 10% | 0.462 | [7 empty] | 559.02 | [7 empty] | 10% | [7 empty] | 10% | 10%
| Headboard | 3 | 3.3 | sqm | 330 | 0 | 330 | 1089 |  | 0.33 | 0.33 | 0.66 | 2.64 | 108.9 | 108.9 | 217.8 | 871.2 | 10% | 0.33 | [7 empty] | 108.9 | [7 empty] | 10% | [7 empty] | 10% | 10%
| Mouldings | 4.3 | 4.73 | Im | 550 | 330 | 880 | 4162.4 |  | 0.473 | 0.473 | 0.946 | 3.784 | 416.24 | 416.24 | 832.48 | 3329.92 | 10% | 0.473 | [7 empty] | 416.24 | [7 empty] | 10% | [7 empty] | 10% | 10%
| BEDROOM 4 |  |  |  | 0 | 0
| Stucco Cement Finish | 37.4 | 41.14 | sqm | 350 | 350 | 700 | 28798 |  | 4.114 | 12.342 | 16.456 | 24.684 | 2879.8 | 8639.4 | 11519.2 | 17278.8 | 30% | 4.114 | [7 empty] | 2879.8 | [7 empty] | 30% | [7 empty] | 10% | 10%
| Headboard | 5.2 | 5.72 | sqm | 330 | 350 | 680 | 3889.6 |  | 0.572 | 1.716 | 2.288 | 3.432 | 388.96 | 1166.88 | 1555.84 | 2333.76 | 30% | 0.572 | [7 empty] | 388.96 | [7 empty] | 30% | [7 empty] | 10% | 10%
| Mouldings | 3.3 | 3.63 | Im | 550 | 330 | 880 | 3194.4 |  | 0.363 | 1.089 | 1.452 | 2.178 | 319.44 | 958.32 | 1277.76 | 1916.64 | 30% | 0.363 | [7 empty] | 319.44 | [7 empty] | 30% | [7 empty] | 10% | 10%
| HALLWAY |  |  |  | 0 | 0 | 0 | 0
| Wall in Semi Gloss off White | 50.6 | 55.66 | sqm | 350 | 350 | 700 | 38962 |  | 5.566 | 33.396 | 38.962 | 16.698 | 3896.2 | 23377.2 | 27273.4 | 11688.6 | 60% | 5.566 | [7 empty] | 3896.2 | [7 empty] | 60% | [7 empty] | 10% | 10%
| T&B |  |  |  | 0 | 0
| White Mosaic Tiles In Semi Gloss Finish | 4 | 4.4 | sqm | 770 | 350 | 1120 | 4928 |  | 0.44 | 1.76 | 2.2 | 2.2 | 492.8 | 1971.2 | 2464 | 2464 | 40% | 0.44 | [7 empty] | 492.8 | [7 empty] | 40% | [7 empty] | 10% | 30%
| 60x60 White Tiles In Marbles in Semi Gloss Finish | 3.7 | 4.07 | sqm | 650 | 350 | 1000 | 4070 |  | 0.6105 | 1.4245 | 2.035 | 2.035 | 610.5 | 1424.5 | 2035 | 2035 | 35% | 0.6105 | [7 empty] | 610.5 | [7 empty] | 35% | [7 empty] | 15% | 30%
| Texturia Interior Film in Wood Finish or Wood Tiles | 18.8 | 20.68 | sqm | 1320 | 700 | 2020 | 41773.6 |  | 3.102 | 8.272 | 11.374 | 9.306 | 6266.04 | 16709.44 | 22975.48 | 18798.12 | 40% | 3.102 | [7 empty] | 6266.04 | [7 empty] | 40% | [7 empty] | 15% | 15%
| Gray Quartz or Synthetic Counter Top | 1.5 | 1.65 | sqm | 6600 | 3300 | 9900 | 16335 |  | 0.2475 | 0.4125 | 0.66 | 0.99 | 2450.25 | 4083.75 | 6534 | 9801 | 25% | 0.2475 | [7 empty] | 2450.25 | [7 empty] | 25% | [7 empty] | 15% | 15%
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 30791.86 |  | 0.15 | 0.6 | 0.75 | 0.25 | 4618.779 | 18475.116 | 23093.895 | 7697.965 | 60% | 0.15 | [7 empty] | 4618.779 | [7 empty] | 60% | [7 empty] | 15% | 15%
| Sub-total for Second Floor (Interior) | [6 empty] | 338710.46 |  | 34.6251 | 135.1245 | 169.7496 | 162.8014 | 38519.569 | 140662.676 | 179182.245 | 159528.215 | 34.52% | 34.6251 | [7 empty] | 38519.569 | [15 empty] | 10.95% | 14.52%
Second Floor ( Exterior )
BALCONY
| Exposed Aggregate Contcrete Cladding | 4.4 | 4.84 | sqm | 350 | 350 | 700 | 3388 |  | 0.484 | 2.904 | 3.388 | 1.452 | 338.8 | 2032.8 | 2371.6 | 1016.4 | 60% | 0.484 | [7 empty] | 338.8 | [7 empty] | 60% | [7 empty] | 10% | 10%
| WPC Fluted Panel | 18.2 | 20.02 | sqm | 960 | 350 | 1310 | 26226.2 |  | 2.002 | 0 | 2.002 | 18.018 | 2622.62 | 0 | 2622.62 | 23603.58 | 0% | 2.002 | [7 empty] | 2622.62 | [7 empty] | 0% | [7 empty] | 10% | 90%
| Wall Piaint Finish ( Off White ) | 52.75 | 58.025 | sqm | 350 | 350 | 700 | 40617.5 |  | 5.8025 | 31.9138 | 37.7163 | 20.3087 | 4061.75 | 22339.625 | 26401.375 | 14216.125 | 55% | 5.8025 | [7 empty] | 4061.75 | [7 empty] | 55% | [7 empty] | 10% | 10%
| Wall Flashing ( Dark Gray ) | 50 | 55 | l.m | 550 | 350 | 900 | 49500 |  | 5.5 | 22 | 27.5 | 27.5 | 4950 | 19800 | 24750 | 24750 | 40% | 5.5 | [7 empty] | 4950 | [7 empty] | 40% | [7 empty] | 10% | 50%
| Natural Limestone Tiles Texture Running Ashlar Pattern | 12.22 | 13.442 | sqm | 950 | 350 | 1300 | 17474.6 |  | 1.3442 | 4.0326 | 5.3768 | 8.0652 | 1747.46 | 5242.38 | 6989.84 | 10484.76 | 30% | 1.3442 | [7 empty] | 1747.46 | [7 empty] | 30% | [7 empty] | 10% | 40%
| Glass Railings 10mm THK | 25.26 | 27.786 | smq | 6300 | 1260 | 7560 | 210062.16 |  | 2.7786 | 2.7786 | 5.5572 | 22.2288 | 21006.216 | 21006.216 | 42012.432 | 168049.728 | 10% | 2.7786 | [7 empty] | 21006.216 | [7 empty] | 10% | [7 empty] | 10% | 10%
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 34726.846 |  | 0.1 | 0.6 | 0.7 | 0.3 | 3472.6846 | 20836.1076 | 24308.7922 | 10418.0538 | 60% | 0.1 | [7 empty] | 3472.6846 | [7 empty] | 60% | [7 empty] | 10% | 20%
| Sub-total For Second Floor (Exterior) | [6 empty] | 381995.306 |  | 18.0113 | 64.229 | 82.2403 | 97.8728 | 38199.5306 | 91257.1286 | 129456.6592 | 252538.6468 | 36.43% | 18.0113 | [7 empty] | 38199.5306 | [15 empty] | 10% | 32.86%
Third Floor ( Interior )
WALK IN CLOSET
| White Semi Gloss | 40.5 | 44.55 | sqm | 350 | 350 | 700 | 31185 |  | 4.455 | 13.365 | 17.82 | 26.73 | 3118.5 | 9355.5 | 12474 | 18711 | 30% | 4.455 | [7 empty] | 3118.5 | [7 empty] | 30% | [7 empty] | 10% | 40%
| MASTER'S BEDROOM |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0 | [7 empty] | 0 | [7 empty] | 30% | [7 empty] | 15% | 30%
| Wall in White Textured Wallpaper Finish | 41.6 | 45.76 | sqm | 350 | 350 | 700 | 32032 |  | 6.864 | 18.304 | 25.168 | 20.592 | 4804.8 | 12812.8 | 17617.6 | 14414.4 | 40% | 6.864 | [7 empty] | 4804.8 | [7 empty] | 40% | [7 empty] | 15% | 15%
| Wall in Wood Fluted Panel Finish | 6.1 | 6.71 | sqm | 1100 | 330 | 1430 | 9595.3 |  | 1.0065 | 2.684 | 3.6905 | 3.0195 | 1439.295 | 3838.12 | 5277.415 | 4317.885 | 40% | 1.0065 | [7 empty] | 1439.295 | [7 empty] | 40% | [7 empty] | 15% | 15%
| MASTER'S T&B |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40% | 0 | [7 empty] | 0 | [7 empty] | 40% | [7 empty] | 15% | 15%
| 60x120 Marbles Tiles in High Gloss Finish | 30.6 | 33.66 | sqm | 450 | 350 | 800 | 26928 |  | 5.049 | 15.147 | 20.196 | 13.464 | 4039.2 | 12117.6 | 16156.8 | 10771.2 | 45% | 5.049 | [7 empty] | 4039.2 | [7 empty] | 45% | [7 empty] | 15% | 30%
| 60x120 Light Biege Tiles in High Gloss Finish | 1 | 1.1 | sqm | 330 | 350 | 680 | 748 |  | 0.165 | 0.495 | 0.66 | 0.44 | 112.2 | 336.6 | 448.8 | 299.2 | 45% | 0.165 | [7 empty] | 112.2 | [7 empty] | 45% | [7 empty] | 15% | 30%
| MEMORABILIA |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0 | [7 empty] | 0 | [7 empty] | 15% | [7 empty] | 15% | 15%
| Wall Cladding in Wood Laminated Finish | 3.6 | 3.96 | sqm | 1100 | 350 | 1450 | 5742 |  | 0.594 | 0.792 | 1.386 | 2.574 | 861.3 | 1148.4 | 2009.7 | 3732.3 | 20% | 0.594 | [7 empty] | 861.3 | [7 empty] | 20% | [7 empty] | 15% | 15%
| Wall in Light Biege Semi- Gloss Painted Finish | 24.2 | 26.62 | sqm | 350 | 350 | 700 | 18634 |  | 3.993 | 13.31 | 17.303 | 9.317 | 2795.1 | 9317 | 12112.1 | 6521.9 | 50% | 3.993 | [7 empty] | 2795.1 | [7 empty] | 50% | [7 empty] | 15% | 10%
| HALLWAY |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0 | [7 empty] | 0 | [7 empty] | 15% | [7 empty] | 15% | 15%
| Wall in Semi Gloss off White Painted Finish | 27.5 | 30.25 | sqm | 350 | 350 | 700 | 21175 |  | 4.5375 | 12.1 | 16.6375 | 13.6125 | 3176.25 | 8470 | 11646.25 | 9528.75 | 40% | 4.5375 | [7 empty] | 3176.25 | [7 empty] | 40% | [7 empty] | 15% | 25%
| VIEWDECK | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40% | 0 | [7 empty] | 0 | [7 empty] | 40% | [7 empty] | 15% | 15%
| Wall in Light Biege Semi- Gloss Painted Finish | 30.26 | 33.286 | sqm | 330 | 350 | 680 | 22634.48 |  | 4.9929 | 6.6572 | 11.6501 | 21.6359 | 3395.172 | 4526.896 | 7922.068 | 14712.412 | 20% | 4.9929 | [7 empty] | 3395.172 | [7 empty] | 20% | [7 empty] | 15% | 15%
| Miscellaneous and other consumables |  | 1 | lot |  |  |  | 14603.93 |  | 0.15 | 0.5 | 0.65 | 0.35 | 2190.5895 | 7301.965 | 9492.5545 | 5111.3755 | 50% | 0.15 | [7 empty] | 2190.5895 | [7 empty] | 50% | [7 empty] | 15% | 25%
| Sub-total For Third Floor (Interior) | [6 empty] | 183277.71 |  | 31.8069 | 83.3542 | 115.1611 | 111.7349 | 25932.4065 | 69224.881 | 95157.2875 | 88120.4225 | 34.67% | 31.8069 | [7 empty] | 25932.4065 | [15 empty] | 14.67% | 20.67%
Third Floor ( Exterior )
BALCONY
| Wall Piaint Finish ( Off White ) | 49.9 | 54.89 | sqm | 350 | 350 | 700 | 38423 |  | 7.1357 | 16.467 | 23.6027 | 31.2873 | 4994.99 | 11526.9 | 16521.89 | 21901.11 | 30% | 7.1357 | [7 empty] | 4994.99 | [7 empty] | 30% | [7 empty] | 13% | 17%
| Natural Limestone Tiles Texture Running Ashlar Pattern | 43.76 | 48.136 | sqm | 950 | 350 | 1300 | 62576.8 |  | 6.2577 | 17.8103 | 24.068 | 24.068 | 8134.984 | 23153.416 | 31288.4 | 31288.4 | 37% | 6.2577 | [7 empty] | 8134.984 | [7 empty] | 37% | [7 empty] | 13% | 50%
| Concrete Cladding With Groove Lines | 67.8 | 74.58 | sqm | 350 | 350 | 700 | 52206 |  | 9.6954 | 14.916 | 24.6114 | 49.9686 | 6786.78 | 10441.2 | 17227.98 | 34978.02 | 20% | 9.6954 | [7 empty] | 6786.78 | [7 empty] | 20% | [7 empty] | 13% | 13%
| Glass Railings 10mm THK | 37.5 | 41.25 | sqm | 6300 | 1260 | 7560 | 311850 |  | 5.3625 | 8.25 | 13.6125 | 27.6375 | 40540.5 | 62370 | 102910.5 | 208939.5 | 20% | 5.3625 | [7 empty] | 40540.5 | [7 empty] | 20% | [7 empty] | 13% | 13%
| Miscellaneous and other consumables | [6 empty] | 46505.58 |  | 0 | 0 | 0 | 0 | 6045.7254 | 18602.232 | 24647.9574 | 21857.6226 | 40% | 0 | [7 empty] | 6045.7254 | [7 empty] | 40% | [7 empty] | 13% | 27%
| Sub-total for Third Floor (Exterior) | [6 empty] | 511561.38 |  | 28.4513 | 57.4433 | 85.8946 | 132.9614 | 66502.9794 | 126093.748 | 192596.7274 | 318964.6526 | 29.4% | 28.4513 | [7 empty] | 66502.9794 | [15 empty] | 13% | 24%
STAIR
| Wall Cladding White Fluted in Ducco Painted Finish | 24.6 | 27.06 | sqm | 550 | 350 | 900 | 24354 |  | 4.059 | 4.059 | 8.118 | 18.942 | 3653.1 | 3653.1 | 7306.2 | 17047.8 | 15% | 4.059 | [7 empty] | 3653.1 | [7 empty] | 15% | [7 empty] | 15% | 15%
| Semi Gloss Off White | 115.8 | 127.38 | sqm | 350 | 350 | 700 | 89166 |  | 19.107 | 50.952 | 70.059 | 57.321 | 13374.9 | 35666.4 | 49041.3 | 40124.7 | 40% | 19.107 | [7 empty] | 13374.9 | [7 empty] | 40% | [7 empty] | 15% | 15%
| Glass Railings 10mm THK | 9.7 | 10.67 | sqm | 6300 | 1260 | 7560 | 80665.2 |  | 1.6005 | 1.6005 | 3.201 | 7.469 | 12099.78 | 12099.78 | 24199.56 | 56465.64 | 15% | 1.6005 | [7 empty] | 12099.78 | [7 empty] | 15% | [7 empty] | 15% | 15%
| Beveled Clear Mirror 10mm THK | 12 | 13.2 | sqm | 1375 | 700 | 2075 | 27390 |  | 1.98 | 1.98 | 3.96 | 9.24 | 4108.5 | 4108.5 | 8217 | 19173 | 15% | 1.98 | [7 empty] | 4108.5 | [7 empty] | 15% | [7 empty] | 15% | 15%
| Miscellaneous and other consumables | [6 empty] | 22157.52 |  | 0 | 0 | 0 | 0 | 3323.628 | 8863.008 | 12186.636 | 9970.884 | 40% | 0 | [7 empty] | 3323.628 | [7 empty] | 40% | [7 empty] | 15% | 15%
| Sub-total For Stair | [6 empty] | 243732.72 |  | 26.7465 | 58.5915 | 85.338 | 92.972 | 36559.908 | 64390.788 | 100950.696 | 142782.024 | 25% | 26.7465 | [7 empty] | 36559.908 | [15 empty] | 15% | 15%
| Total For Wall Finish | [6 empty] | 2040984.176 |  | 181.1703 | 546.0237 | 727.194 | 730.0041 | 257997.3385 | 655611.8976 | 913609.2361 | 1127374.9399 | 34.31% | 181.1703 | [7 empty] | 257997.3385 | [15 empty] | 12.76% | 19.56%

## CABINETS
Project name : | PROPOSED THREE STORY RESIDENCE
Location : | GRAND CENTENIAL HOMES KAWIT CAVITE
Date : | 2026-08-17
[27 empty] | QUANTITY | [7 empty] | AMOUNT | [7 empty] | ACCOMPLISHMENT | PREVIOUS ACCOMPLISHMENT
ITEM NO | Description | QUANTITY | QUANTITY | UNIT | Material Cost Php/unit | Labor and Equipment Cost Php/unit | Total Cost Php/Unit | Total Amount Php | [8 empty] | QUANTITY |  |  |  | AMOUNT |  |  |  | PERCENTAGE |  | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | BILLING | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8
| Cabinets | [15 empty] | PREVIOUS | THIS DATE | TO DATE | BALANCE | PREVIOUS | THIS DATE | TO DATE | BALANCE | Accomplishment
GROUND FLOOR
LIving Area ( Tv rack with Cabinets )
| UV Board Marble | 6.7 | 7.37 | sq.m | 555 | 300 | 855 | 6301.35 | [8 empty] | 0 | 2.211 | 2.211 | 5.159 | 0 | 1890.405 | 1890.405 | 4410.945 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3/4'' Marine Plywood | 45.74 | 50.314 | sq.m | 576 | 300 | 876 | 44075.064 |  | Multiplier Mark up | [6 empty] | 0 | 15.0942 | 15.0942 | 35.2198 | 0 | 13222.5192 | 13222.5192 | 30852.5448 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Pvc Fluted Panels | 5 | 5.5 | sq.m | 880 | 450 | 1330 | 7315 |  | 1.1 | [6 empty] | 0 | 0 | 0 | 5.5 | 0 | 0 | 0 | 7315 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 12 | 13.2 | sq.m | 330 | 165 | 495 | 6534 | [8 empty] | 0 | 0 | 0 | 13.2 | 0 | 0 | 0 | 6534 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 2.31 | 2.541 | l.m | 220 | 110 | 330 | 838.53 | [8 empty] | 0 | 0 | 0 | 2.541 | 0 | 0 | 0 | 838.53 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Paint Finish | 34.04 | 37.444 | sq.m | 555 | 275 | 830 | 31078.52 |  | Miscellaneous | [6 empty] | 0 | 0 | 0 | 37.444 | 0 | 0 | 0 | 31078.52 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 11537.0957 |  | 0.12 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 11537.0957 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| LIving Area ( Tv rack with Cabinets ) Sub-total: | [6 empty] | 107679.5597 |  | 0.8 | [6 empty] | 0 | 17.3052 | 17.3052 | 100.0638 | 0 | 15112.9242 | 15112.9242 | 92566.6355 | 8.571% |  | 0 | [15 empty] | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| LIving Area ( Storage Cabinets ) | [23 empty] | 0%
| 3/4'' Marine Plywood | 7.9 | 8.69 | sq.m | 576 | 300 | 876 | 7612.44 | [8 empty] | 0 | 2.607 | 2.607 | 6.083 | 0 | 2283.732 | 2283.732 | 5328.708 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 2.1 | 2.31 | sq.m | 330 | 165 | 495 | 1143.45 | [8 empty] | 0 | 0.693 | 0.693 | 1.617 | 0 | 343.035 | 343.035 | 800.415 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Paint Finish | 3.94 | 4.334 | sq.m | 555 | 275 | 830 | 3597.22 | [8 empty] | 0 | 0 | 0 | 4.334 | 0 | 0 | 0 | 3597.22 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 3.96 | 4.356 | sq.m | 555 | 275 | 830 | 3615.48 | [8 empty] | 0 | 0 | 0 | 4.356 | 0 | 0 | 0 | 3615.48 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 7984.295 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 7984.295 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| LIving Area ( Storage Cabinets ) Sub-total: | [6 empty] | 23952.885 | [8 empty] | 0 | 3.3 | 3.3 | 17.39 | 0 | 2626.767 | 2626.767 | 21326.118 | 12% | 0 | 0 | [15 empty] | 12% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Kitchen Area ( Storage Cabinets ) | [23 empty] | 0%
| 3/4'' Marine Plywood | 62.89 | 69.179 | sq.m | 576 | 300 | 876 | 60600.804 | [8 empty] | 0 | 20.7537 | 20.7537 | 48.4253 | 0 | 18180.2412 | 18180.2412 | 42420.5628 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 7.9 | 8.69 | sq.m | 330 | 165 | 495 | 4301.55 | [8 empty] | 0 | 2.607 | 2.607 | 6.083 | 0 | 1290.465 | 1290.465 | 3011.085 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Paint Finish | 50.312 | 55.3432 | sq.m | 555 | 275 | 830 | 45934.856 | [8 empty] | 0 | 0 | 0 | 55.3432 | 0 | 0 | 0 | 45934.856 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Quartz White sintered stone | 1.79 | 1.969 | sq.m | 6600 | 3300 | 9900 | 19493.1 | [8 empty] | 0 | 0 | 0 | 1.969 | 0 | 0 | 0 | 19493.1 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 15639.6372 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 15639.6372 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Kitchen Area ( Storage Cabinets ) Sub-total: | [6 empty] | 145969.9472 | [8 empty] | 0 | 23.3607 | 23.3607 | 112.8205 | 0 | 19470.7062 | 19470.7062 | 126499.241 | 12% |  | 0 | [15 empty] | 12% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Kitchen Area ( Counter Top ) | [23 empty] | 0%
| 3/4'' Marine Plywood | 18.04 | 19.844 | sq.m | 576 | 300 | 876 | 17383.344 | [8 empty] | 0 | 5.9532 | 5.9532 | 13.8908 | 0 | 5215.0032 | 5215.0032 | 12168.3408 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 2.6 | 2.86 | sq.m | 330 | 165 | 495 | 1415.7 | [8 empty] | 0 | 0.858 | 0.858 | 2.002 | 0 | 424.71 | 424.71 | 990.99 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Paint Finish | 15.44 | 16.984 | sq.m | 555 | 275 | 830 | 14096.72 | [8 empty] | 0 | 0 | 0 | 16.984 | 0 | 0 | 0 | 14096.72 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Quartz White sintered stone | 5.4 | 5.94 | sq.m | 6600 | 3300 | 9900 | 58806 | [8 empty] | 0 | 0 | 0 | 5.94 | 0 | 0 | 0 | 58806 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 11004.2117 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 11004.2117 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Kitchen Area ( Counter Top ) Sub-total: | [6 empty] | 102705.9757 | [8 empty] | 0 | 6.8112 | 6.8112 | 39.8168 | 0 | 5639.7132 | 5639.7132 | 97066.2625 | 12% |  | 0 | [15 empty] | 12% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Powder Room (Lavatory Cabinets) | [23 empty] | 0%
| 3/4'' Marine Plywood | 4.46 | 4.906 | sq.m | 576 | 300 | 876 | 4297.656 |  | Miscellaneous | [6 empty] | 0 | 3.9248 | 3.9248 | 0.9812 | 0 | 3438.1248 | 3438.1248 | 859.5312 | 80% |  | 0 | [15 empty] | 80% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 0.6 | 0.66 | sq.m | 330 | 165 | 495 | 326.7 |  | 0.4 | [6 empty] | 0 | 0.528 | 0.528 | 0.132 | 0 | 261.36 | 261.36 | 65.34 | 80% |  | 0 | [15 empty] | 80% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 3.56 | 3.916 | sq.m | 555 | 275 | 830 | 3250.28 | [8 empty] | 0 | 0.7832 | 0.7832 | 3.1328 | 0 | 650.056 | 650.056 | 2600.224 | 20% |  | 0 | [15 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Quartz White sintered stone | 0.45 | 0.495 | sq.m | 6600 | 3300 | 9900 | 4900.5 | [8 empty] | 0 | 0.099 | 0.099 | 0.396 | 0 | 980.1 | 980.1 | 3920.4 | 20% |  | 0 | [15 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 5110.0544 | [8 empty] | 0 | 0.6 | 0.6 | 0.4 | 0 | 3066.0326 | 3066.0326 | 2044.0218 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Powder Room Sub-total: | [6 empty] | 17885.1904 | [8 empty] | 0 | 5.935 | 5.935 | 5.042 | 0 | 8395.6734 | 8395.6734 | 9489.517 | 52% |  | 0 | [15 empty] | 52% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Office (Shelves with Cabinets and table) | [23 empty] | 0%
| 1''x1''x2.0mm Tubular Steel | 12 | 13.2 | l.m | 70.18 | 35.09 | 105.27 | 1389.564 | [8 empty] | 0 | 5.28 | 5.28 | 7.92 | 0 | 555.8256 | 555.8256 | 833.7384 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3/4'' Marine Plywood | 11.18 | 12.298 | sq.m | 576 | 300 | 876 | 10773.048 | [8 empty] | 0 | 4.9192 | 4.9192 | 7.3788 | 0 | 4309.2192 | 4309.2192 | 6463.8288 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 1.1 | 1.21 | sq.m | 330 | 165 | 495 | 598.95 | [8 empty] | 0 | 0.484 | 0.484 | 0.726 | 0 | 239.58 | 239.58 | 359.37 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| PVC Board | 1.58 | 1.738 | sq.m | 748 | 380 | 1128 | 1960.464 | [8 empty] | 0 | 0.6952 | 0.6952 | 1.0428 | 0 | 784.1856 | 784.1856 | 1176.2784 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer Laminate | 13 | 14.3 | sq.m | 2640 | 380 | 3020 | 43186 | [8 empty] | 0 | 5.72 | 5.72 | 8.58 | 0 | 17274.4 | 17274.4 | 25911.6 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer Edge Laminate | 20.02 | 22.022 | l.m | 55 | 30 | 85 | 1871.87 | [8 empty] | 0 | 8.8088 | 8.8088 | 13.2132 | 0 | 748.748 | 748.748 | 1123.122 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Coated Powder (Black) | 10 | 11 | sq.m | 275 | 140 | 415 | 4565 | [8 empty] | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 4565 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 2.31 | 2.541 | l.m | 220 | 110 | 330 | 838.53 | [8 empty] | 0 | 0 | 0 | 2.541 | 0 | 0 | 0 | 838.53 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 7822.0111 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 7822.0111 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Office (Shelves with Cabinets and table) Sub-total: | [6 empty] | 73005.4371 | [8 empty] | 0 | 25.9072 | 25.9072 | 53.4018 | 0 | 23911.9584 | 23911.9584 | 49093.4787 | 26.67% |  | 0 | [15 empty] | 26.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ground Floor Cabinet's Sub-total: | [6 empty] | 471198.9951 | [8 empty] | 0 | 82.6193 | 82.6193 | 328.5349 | 0 | 75157.7424 | 75157.7424 | 396041.2526 | 20.54% |  | 0 | [15 empty] | 20.54% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| SECOND FLOOR | [23 empty] | 0%
| Hallway (cabinets) | [23 empty] | 0%
| 3/4'' Marine Plywood | 6.77 | 7.447 | sq.m | 576 | 300 | 876 | 6523.572 |  | Miscellaneous | [6 empty] | 0 | 2.9788 | 2.9788 | 4.4682 | 0 | 2609.4288 | 2609.4288 | 3914.1432 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 1.1 | 1.21 | sq.m | 330 | 165 | 495 | 598.95 |  | 0.5 | [6 empty] | 0 | 0.484 | 0.484 | 0.726 | 0 | 239.58 | 239.58 | 359.37 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 6.77 | 7.447 | sq.m | 555 | 275 | 830 | 6181.01 | [8 empty] | 0 | 2.9788 | 2.9788 | 4.4682 | 0 | 2472.404 | 2472.404 | 3708.606 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 6651.766 | [8 empty] | 0 | 0.2 | 0.2 | 0.8 | 0 | 1330.3532 | 1330.3532 | 5321.4128 | 20% |  | 0 | [15 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Hallway (cabinets) Sub-total: | [6 empty] | 19955.298 | [8 empty] | 0 | 6.6416 | 6.6416 | 10.4624 | 0 | 6651.766 | 6651.766 | 13303.532 | 35% |  | 0 | [15 empty] | 35% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 1 (Closets) | [23 empty] | 0%
| 3/4'' Marine Plywood | 23.4 | 25.74 | sq.m | 576 | 300 | 876 | 22548.24 | [8 empty] | 0 | 25.74 | 25.74 | 0 | 0 | 22548.24 | 22548.24 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 7 | 7.7 | sq.m | 330 | 165 | 495 | 3811.5 | [8 empty] | 0 | 7.7 | 7.7 | 0 | 0 | 3811.5 | 3811.5 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Stainless Hanging Rod | 4.8 | 5.28 | l.m | 330 | 165 | 495 | 2613.6 | [8 empty] | 0 | 0 | 0 | 5.28 | 0 | 0 | 0 | 2613.6 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 2.4 | 2.64 | l.m | 220 | 110 | 330 | 871.2 | [8 empty] | 0 | 0 | 0 | 2.64 | 0 | 0 | 0 | 871.2 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 21.66 | 23.826 | sq.m | 555 | 275 | 830 | 19775.58 | [8 empty] | 0 | 7.1478 | 7.1478 | 16.6782 | 0 | 5932.674 | 5932.674 | 13842.906 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 5954.4144 | [8 empty] | 0 | 0.3 | 0.3 | 0.7 | 0 | 1786.3243 | 1786.3243 | 4168.0901 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 1 (Closets) Sub-total: | [6 empty] | 55574.5344 | [8 empty] | 0 | 40.8878 | 40.8878 | 25.2982 | 0 | 34078.7383 | 34078.7383 | 21495.7961 | 43.33% |  | 0 | [15 empty] | 43.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 1 (Table & Top Cabinets) | [23 empty] | 0%
| 3/4'' Marine Plywood | 23.41 | 25.751 | sq.m | 576 | 300 | 876 | 22557.876 | [8 empty] | 0 | 25.751 | 25.751 | 0 | 0 | 22557.876 | 22557.876 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 3.4 | 3.74 | sq.m | 330 | 165 | 495 | 1851.3 | [8 empty] | 0 | 3.74 | 3.74 | 0 | 0 | 1851.3 | 1851.3 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Vanity Lights |  | 8 | pcs | 220 | 110 | 330 | 2640 | [8 empty] | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 2640 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Mirror | 1.22 | 1.342 | sq.m | 1265 | 640 | 1905 | 2556.51 | [8 empty] | 0 | 0 | 0 | 1.342 | 0 | 0 | 0 | 2556.51 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 18.73 | 20.603 | sq.m | 555 | 275 | 830 | 17100.49 | [8 empty] | 0 | 12.3618 | 12.3618 | 8.2412 | 0 | 10260.294 | 10260.294 | 6840.196 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 5604.7411 | [8 empty] | 0 | 0.6 | 0.6 | 0.4 | 0 | 3362.8447 | 3362.8447 | 2241.8964 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 1 (Table & Top Cabinets) Sub-total: | [6 empty] | 52310.9171 | [8 empty] | 0 | 42.4528 | 42.4528 | 17.9832 | 0 | 38032.3147 | 38032.3147 | 14278.6024 | 53.33% |  | 0 | [15 empty] | 53.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 2 (Closets) | [23 empty] | 0%
| 3/4'' Marine Plywood | 30.24 | 33.264 | sq.m | 576 | 300 | 876 | 29139.264 | [8 empty] | 0 | 33.264 | 33.264 | 0 | 0 | 29139.264 | 29139.264 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 7.8 | 8.58 | sq.m | 330 | 165 | 495 | 4247.1 | [8 empty] | 0 | 8.58 | 8.58 | 0 | 0 | 4247.1 | 4247.1 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Stainless Hanging Rod | 4.4 | 4.84 | l.m | 330 | 165 | 495 | 2395.8 | [8 empty] | 0 | 0 | 0 | 4.84 | 0 | 0 | 0 | 2395.8 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 2.7 | 2.97 | l.m | 220 | 110 | 330 | 980.1 | [8 empty] | 0 | 0 | 0 | 2.97 | 0 | 0 | 0 | 980.1 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 22 | 24.2 | sq.m | 555 | 275 | 830 | 20086 | [8 empty] | 0 | 14.52 | 14.52 | 9.68 | 0 | 12051.6 | 12051.6 | 8034.4 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 6821.7917 | [8 empty] | 0 | 0.6 | 0.6 | 0.4 | 0 | 4093.075 | 4093.075 | 2728.7167 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 2 (Closets) Sub-total: | [6 empty] | 63670.0557 | [8 empty] | 0 | 56.964 | 56.964 | 17.89 | 0 | 49531.039 | 49531.039 | 14139.0167 | 53.33% |  | 0 | [15 empty] | 53.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 2 (Table & Top Cabinets) | [23 empty] | 0%
| 3/4'' Marine Plywood | 10.3992 | 11.4391 | sq.m | 576 | 300 | 876 | 10020.6691 | [8 empty] | 0 | 11.4391 | 11.4391 | 0 | 0 | 10020.6691 | 10020.6691 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 2.4 | 2.64 | sq.m | 330 | 165 | 495 | 1306.8 | [8 empty] | 0 | 2.64 | 2.64 | 0 | 0 | 1306.8 | 1306.8 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 2''x1''x2.0mm Tubular Steel | 2.2 | 2.42 | l.m | 70.18 | 35.09 | 105.27 | 254.7534 | [8 empty] | 0 | 0.484 | 0.484 | 1.936 | 0 | 50.9507 | 50.9507 | 203.8027 | 20% |  | 0 | [15 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 1.62 | 1.782 | l.m | 220 | 110 | 330 | 588.06 | [8 empty] | 0 | 0.3564 | 0.3564 | 1.4256 | 0 | 117.612 | 117.612 | 470.448 | 20% |  | 0 | [15 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 7.28 | 8.008 | sq.m | 555 | 275 | 830 | 6646.64 | [8 empty] | 0 | 4.8048 | 4.8048 | 3.2032 | 0 | 3987.984 | 3987.984 | 2658.656 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 9408.4613 | [8 empty] | 0 | 0.6 | 0.6 | 0.4 | 0 | 5645.0768 | 5645.0768 | 3763.3845 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 2 (Table & Top Cabinets) Sub-total: | [6 empty] | 28225.3838 | [8 empty] | 0 | 20.3243 | 20.3243 | 6.9648 | 0 | 21129.0926 | 21129.0926 | 7096.2912 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 3 (Closets) | [23 empty] | 0%
| 3/4'' Marine Plywood | 24.72 | 27.192 | sq.m | 576 | 300 | 876 | 23820.192 | [8 empty] | 0 | 27.192 | 27.192 | 0 | 0 | 23820.192 | 23820.192 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 6.4 | 7.04 | sq.m | 330 | 165 | 495 | 3484.8 | [8 empty] | 0 | 7.04 | 7.04 | 0 | 0 | 3484.8 | 3484.8 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Stainless Hanging Rod | 4.6 | 5.06 | l.m | 330 | 165 | 495 | 2504.7 | [8 empty] | 0 | 0 | 0 | 5.06 | 0 | 0 | 0 | 2504.7 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 2.3 | 2.53 | l.m | 220 | 110 | 330 | 834.9 | [8 empty] | 0 | 0 | 0 | 2.53 | 0 | 0 | 0 | 834.9 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 19.78 | 21.758 | sq.m | 555 | 275 | 830 | 18059.14 | [8 empty] | 0 | 6.5274 | 6.5274 | 15.2306 | 0 | 5417.742 | 5417.742 | 12641.398 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 5844.4478 | [8 empty] | 0 | 0.4 | 0.4 | 0.6 | 0 | 2337.7791 | 2337.7791 | 3506.6687 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 3 (Closets) Sub-total: | [6 empty] | 54548.1798 | [8 empty] | 0 | 41.1594 | 41.1594 | 23.4206 | 0 | 35060.5131 | 35060.5131 | 19487.6667 | 45% |  | 0 | [15 empty] | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 3 (Table & Top Cabinets) | [23 empty] | 0%
| 3/4'' Marine Plywood | 10.36 | 11.396 | sq.m | 576 | 300 | 876 | 9982.896 | [8 empty] | 0 | 11.396 | 11.396 | 0 | 0 | 9982.896 | 9982.896 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 3.5 | 3.85 | sq.m | 330 | 165 | 495 | 1905.75 | [8 empty] | 0 | 3.85 | 3.85 | 0 | 0 | 1905.75 | 1905.75 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Vanity Lights |  | 6 | pcs | 220 | 110 | 330 | 1980 | [8 empty] | 0 | 1.8 | 1.8 | 4.2 | 0 | 594 | 594 | 1386 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Mirror | 1.4 | 1.54 | sq.m | 1265 | 640 | 1905 | 2933.7 | [8 empty] | 0 | 0.154 | 0.154 | 1.386 | 0 | 293.37 | 293.37 | 2640.33 | 10% |  | 0 | [15 empty] | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 2.4 | 2.64 | l.m | 220 | 110 | 330 | 871.2 | [8 empty] | 0 | 0.264 | 0.264 | 2.376 | 0 | 87.12 | 87.12 | 784.08 | 10% |  | 0 | [15 empty] | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer laminated | 2.5 | 2.75 | sq.m | 2640 | 880 | 3520 | 9680 | [8 empty] | 0 | 0.275 | 0.275 | 2.475 | 0 | 968 | 968 | 8712 | 10% |  | 0 | [15 empty] | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer Edge Laminate | 9.6 | 10.56 | l.m | 55 | 30 | 85 | 897.6 | [8 empty] | 0 | 1.056 | 1.056 | 9.504 | 0 | 89.76 | 89.76 | 807.84 | 10% |  | 0 | [15 empty] | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 8.288 | 9.1168 | sq.m | 555 | 275 | 830 | 7566.944 | [8 empty] | 0 | 5.4701 | 5.4701 | 3.6467 | 0 | 4540.1664 | 4540.1664 | 3026.7776 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 17909.045 | [8 empty] | 0 | 0.6 | 0.6 | 0.4 | 0 | 10745.427 | 10745.427 | 7163.618 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 3 (Table & Top Cabinets) Sub-total: | [6 empty] | 53727.135 | [8 empty] | 0 | 24.8651 | 24.8651 | 23.9877 | 0 | 29206.4894 | 29206.4894 | 24520.6456 | 43.33% |  | 0 | [15 empty] | 43.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 4 (Table, shelves & Top Cabinets) | [23 empty] | 0%
| 3/4'' Marine Plywood | 26.12 | 28.732 | sq.m | 576 | 300 | 876 | 25169.232 | [8 empty] | 0 | 28.732 | 28.732 | 0 | 0 | 25169.232 | 25169.232 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 4.9 | 5.39 | sq.m | 330 | 165 | 495 | 2668.05 | [8 empty] | 0 | 5.39 | 5.39 | 0 | 0 | 2668.05 | 2668.05 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Vanity Lights |  | 6 | pcs | 220 | 110 | 330 | 1980 | [8 empty] | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 1980 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Mirror | 1.5 | 1.65 | sq.m | 1265 | 640 | 1905 | 3143.25 | [8 empty] | 0 | 0 | 0 | 1.65 | 0 | 0 | 0 | 3143.25 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 2 | 2.2 | l.m | 220 | 110 | 330 | 726 | [8 empty] | 0 | 0 | 0 | 2.2 | 0 | 0 | 0 | 726 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer laminated | 31.02 | 34.122 | sq.m | 2640 | 880 | 3520 | 120109.44 | [8 empty] | 0 | 34.122 | 34.122 | 0 | 0 | 120109.44 | 120109.44 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer Edge Laminate | 41.1 | 45.21 | l.m | 55 | 30 | 85 | 3842.85 | [8 empty] | 0 | 45.21 | 45.21 | 0 | 0 | 3842.85 | 3842.85 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 2.1 | 2.31 | sq.m | 555 | 275 | 830 | 1917.3 | [8 empty] | 0 | 2.31 | 2.31 | 0 | 0 | 1917.3 | 1917.3 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 19146.7346 | [8 empty] | 0 | 0.7 | 0.7 | 0.3 | 0 | 13402.7142 | 13402.7142 | 5744.0204 | 70% |  | 0 | [15 empty] | 70% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 4 (Table, shelves & Top Cabinets) Sub-total: | [6 empty] | 178702.8566 | [8 empty] | 0 | 116.464 | 116.464 | 10.15 | 0 | 167109.5862 | 167109.5862 | 11593.2704 | 63.33% |  | 0 | [15 empty] | 63.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 4 (Closet) | [23 empty] | 0%
| 3/4'' Marine Plywood | 24.92 | 27.412 | sq.m | 576 | 300 | 876 | 24012.912 |  | 21.8 | [6 empty] | 0 | 0 | 0 | 27.412 | 0 | 0 | 0 | 24012.912 | 0% |  | 0 | [15 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 5.4 | 5.94 | sq.m | 330 | 165 | 495 | 2940.3 |  | 3.8 | [6 empty] | 0 | 0 | 0 | 5.94 | 0 | 0 | 0 | 2940.3 | 0% |  | 0 | [15 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer laminated | 30.32 | 33.352 | sq.m | 2640 | 880 | 3520 | 117399.04 | [8 empty] | 0 | 23.3464 | 23.3464 | 10.0056 | 0 | 82179.328 | 82179.328 | 35219.712 | 70% |  | 0 | [15 empty] | 70% | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
| Wood Slatted Door | 2.4 | 2.64 | sq.m | 550 | 275 | 825 | 2178 | [8 empty] | 0 | 1.848 | 1.848 | 0.792 | 0 | 1524.6 | 1524.6 | 653.4 | 70% |  | 0 | [15 empty] | 70% | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer Edge Laminate | 21.8 | 23.98 | l.m | 55 | 30 | 85 | 2038.3 | [8 empty] | 0 | 23.98 | 23.98 | 0 | 0 | 2038.3 | 2038.3 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 2.8 | 3.08 | sq.m | 555 | 275 | 830 | 2556.4 | [8 empty] | 0 | 3.08 | 3.08 | 0 | 0 | 2556.4 | 2556.4 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 18134.9942 | [8 empty] | 0 | 0.6 | 0.6 | 0.4 | 0 | 10880.9965 | 10880.9965 | 7253.9977 | 60% |  | 0 | [15 empty] | 60% | 0% | 40% | 0% | 0% | 0% | 0% | 0% | 0%
| Bedroom 4 (Closet) Sub-total: | [6 empty] | 169259.9462 | [8 empty] | 0 | 52.8544 | 52.8544 | 44.5496 | 0 | 99179.6245 | 99179.6245 | 70080.3217 | 57.14% |  | 0 | [15 empty] | 57.14% | 0% | 42.86% | 0% | 0% | 0% | 0% | 0% | 0%
| Common toilet & Bath (2nd Floor) | [23 empty] | 0%
| 3/4'' Marine Plywood | 8.1 | 8.91 | sq.m | 576 | 300 | 876 | 7805.16 | [8 empty] | 0 | 8.91 | 8.91 | 0 | 0 | 7805.16 | 7805.16 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 2.33 | 2.563 | sq.m | 330 | 165 | 495 | 1268.685 | [8 empty] | 0 | 1.7941 | 1.7941 | 0.7689 | 0 | 888.0795 | 888.0795 | 380.6055 | 70% |  | 0 | [15 empty] | 70% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer laminated | 10.43 | 11.473 | sq.m | 2640 | 880 | 3520 | 40384.96 | [8 empty] | 0 | 0 | 0 | 11.473 | 0 | 0 | 0 | 40384.96 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Quartz White sintered stone | 1.1 | 1.21 | sq.m | 6600 | 3300 | 9900 | 11979 | [8 empty] | 0 | 0 | 0 | 1.21 | 0 | 0 | 0 | 11979 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer Edge Laminate | 18.4 | 20.24 | l.m | 55 | 30 | 85 | 1720.4 | [8 empty] | 0 | 4.048 | 4.048 | 16.192 | 0 | 344.08 | 344.08 | 1376.32 | 20% |  | 0 | [15 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 7578.9846 | [8 empty] | 0 | 0.3 | 0.3 | 0.7 | 0 | 2273.6954 | 2273.6954 | 5305.2892 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Common toilet & Bath (2nd Floor) Sub-total: | [6 empty] | 70737.1896 | [8 empty] | 0 | 15.0521 | 15.0521 | 30.3439 | 0 | 11311.0149 | 11311.0149 | 59426.1747 | 36.67% |  | 0 | [15 empty] | 36.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Second Floor Cabinet's Sub-total: | [6 empty] | 746711.4963 | [8 empty] | 0 | 417.6655 | 417.6655 | 211.0504 | 0 | 491290.1788 | 491290.1788 | 255421.3175 | 49.05% |  | 0 | [15 empty] | 49.05% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0%
| THIRD FLOOR | [23 empty] | 0%
| Master's Bedroom ( Cabinet Detail 1) | [23 empty] | 0%
| 3/4'' Marine Plywood | 13.05 | 14.355 | sq.m | 576 | 300 | 876 | 12574.98 | [8 empty] | 0 | 0 | 0 | 14.355 | 0 | 0 | 0 | 12574.98 | 0% |  | 0 | [15 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 1.2 | 1.32 | sq.m | 330 | 165 | 495 | 653.4 | [8 empty] | 0 | 0 | 0 | 1.32 | 0 | 0 | 0 | 653.4 | 0% |  | 0 | [15 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer laminated | 14.25 | 15.675 | sq.m | 2640 | 880 | 3520 | 55176 | 1217910.4914 | [7 empty] | 0 | 10.9725 | 10.9725 | 4.7025 | 0 | 38623.2 | 38623.2 | 16552.8 | 70% |  | 0 | [15 empty] | 70% | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer Edge Laminate | 11.2 | 12.32 | l.m | 55 | 30 | 85 | 1047.2 | [8 empty] | 0 | 8.624 | 8.624 | 3.696 | 0 | 733.04 | 733.04 | 314.16 | 70% |  | 0 | [15 empty] | 70% | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 8334.1896 | [8 empty] | 0 | 0.4 | 0.4 | 0.6 | 0 | 3333.6758 | 3333.6758 | 5000.5138 | 40% |  | 0 | [15 empty] | 40% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom ( Cabinet Detail 1) Sub-total: | [6 empty] | 77785.7696 | [8 empty] | 0 | 19.9965 | 19.9965 | 24.6735 | 0 | 42689.9158 | 42689.9158 | 35095.8538 | 36% |  | 0 | [15 empty] | 36% | 0% | 64% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (Console Cabinet) | [23 empty] | 0%
| 3/4'' Marine Plywood | 14.2 | 15.62 | sq.m | 576 | 300 | 876 | 13683.12 | [8 empty] | 0 | 0 | 0 | 15.62 | 0 | 0 | 0 | 13683.12 | 0% |  | 0 | [15 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 2 | 2.2 | sq.m | 330 | 165 | 495 | 1089 | [8 empty] | 0 | 0 | 0 | 2.2 | 0 | 0 | 0 | 1089 | 0% |  | 0 | [15 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer laminated | 14.2 | 15.62 | sq.m | 2640 | 880 | 3520 | 54982.4 | [8 empty] | 0 | 10.934 | 10.934 | 4.686 | 0 | 38487.68 | 38487.68 | 16494.72 | 70% |  | 0 | [15 empty] | 70% | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer Edge Laminate | 15 | 16.5 | l.m | 55 | 30 | 85 | 1402.5 | [8 empty] | 0 | 11.55 | 11.55 | 4.95 | 0 | 981.75 | 981.75 | 420.75 | 70% |  | 0 | [15 empty] | 70% | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 8538.8424 | [8 empty] | 0 | 0.3 | 0.3 | 0.7 | 0 | 2561.6527 | 2561.6527 | 5977.1897 | 30% |  | 0 | [15 empty] | 30% | 0% | 70% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom ( Cabinet Detail 1) Sub-total: | [6 empty] | 79695.8624 | [8 empty] | 0 | 22.784 | 22.784 | 28.156 | 0 | 42031.0827 | 42031.0827 | 37664.7797 | 34% |  | 0 | [15 empty] | 34% | 0% | 66% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (Walk in closet 1) | [23 empty] | 0%
| 3/4'' Marine Plywood | 46.16 | 50.776 | sq.m | 576 | 300 | 876 | 44479.776 | [8 empty] | 0 | 50.776 | 50.776 | 0 | 0 | 44479.776 | 44479.776 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 12 | 13.2 | sq.m | 330 | 165 | 495 | 6534 | [8 empty] | 0 | 13.2 | 13.2 | 0 | 0 | 6534 | 6534 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Stainless Hanging Rod | 2.9 | 3.19 | l.m | 330 | 165 | 495 | 1579.05 | [8 empty] | 0 | 0 | 0 | 3.19 | 0 | 0 | 0 | 1579.05 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 2.9 | 3.19 | l.m | 220 | 110 | 330 | 1052.7 | [8 empty] | 0 | 0 | 0 | 3.19 | 0 | 0 | 0 | 1052.7 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Clear Glass Door Gold framing | 10 | 11 | sq.m | 6600 | 3300 | 9900 | 108900 | [8 empty] | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 108900 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 58.16 | 63.976 | sq.m | 555 | 275 | 830 | 53100.08 | [8 empty] | 0 | 19.1928 | 19.1928 | 44.7832 | 0 | 15930.024 | 15930.024 | 37170.056 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 25877.4727 | [8 empty] | 0 | 0.3 | 0.3 | 0.7 | 0 | 7763.2418 | 7763.2418 | 18114.2309 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (Walk in closet 1)Sub-total: | [6 empty] | 241523.0787 |  |  |  | 17.1 |  |  |  |  | 0 | 83.4688 | 83.4688 | 62.8632 | 0 | 74707.0418 | 74707.0418 | 166816.0369 | 37.14% |  | 0 | [15 empty] | 37.14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (Walk in closet 2) | [23 empty] | 0%
| 3/4'' Marine Plywood | 33.6 | 36.96 | sq.m | 576 | 300 | 876 | 32376.96 | [8 empty] | 0 | 36.96 | 36.96 | 0 | 0 | 32376.96 | 32376.96 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 5.8 | 6.38 | sq.m | 330 | 165 | 495 | 3158.1 | [8 empty] | 0 | 6.38 | 6.38 | 0 | 0 | 3158.1 | 3158.1 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 4.2 | 4.62 | l.m | 220 | 110 | 330 | 1524.6 | [8 empty] | 0 | 0 | 0 | 4.62 | 0 | 0 | 0 | 1524.6 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Mirror | 1.3 | 1.43 | sq.m | 1265 | 640 | 1905 | 2724.15 | [8 empty] | 0 | 0 | 0 | 1.43 | 0 | 0 | 0 | 2724.15 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Clear Glass Door Gold framing | 3.6 | 3.96 | sq.m | 6600 | 3300 | 9900 | 39204 | [8 empty] | 0 | 0 | 0 | 3.96 | 0 | 0 | 0 | 39204 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 39.4 | 43.34 | sq.m | 555 | 275 | 830 | 35972.2 | [8 empty] | 0 | 17.336 | 17.336 | 26.004 | 0 | 14388.88 | 14388.88 | 21583.32 | 40% |  | 0 | [15 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 13795.2012 |  |  |  | 10 |  |  |  |  | 0 | 0.6 | 0.6 | 0.4 | 0 | 8277.1207 | 8277.1207 | 5518.0805 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (Walk in closet 2)Sub-total: | [6 empty] | 128755.2112 | [8 empty] | 0 | 61.276 | 61.276 | 36.414 | 0 | 58201.0607 | 58201.0607 | 70554.1505 | 42.86% |  | 0 | [15 empty] | 42.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (Walk in closet 3) | [23 empty] | 0%
| 3/4'' Marine Plywood | 31 | 34.1 | sq.m | 576 | 300 | 876 | 29871.6 | [8 empty] | 0 | 34.1 | 34.1 | 0 | 0 | 29871.6 | 29871.6 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 6 | 6.6 | sq.m | 330 | 165 | 495 | 3267 | [8 empty] | 0 | 6.6 | 6.6 | 0 | 0 | 3267 | 3267 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 2 | 2.2 | l.m | 220 | 110 | 330 | 726 | [8 empty] | 0 | 0 | 0 | 2.2 | 0 | 0 | 0 | 726 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Stainless Hanging Rod | 2 | 2.2 | l.m | 330 | 165 | 495 | 1089 | [8 empty] | 0 | 0 | 0 | 2.2 | 0 | 0 | 0 | 1089 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Clear Glass Door Gold framing | 3.9 | 4.29 | sq.m | 6600 | 3300 | 9900 | 42471 | [8 empty] | 0 | 0 | 0 | 4.29 | 0 | 0 | 0 | 42471 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 37 | 40.7 | sq.m | 555 | 275 | 830 | 33781 | [8 empty] | 0 | 24.42 | 24.42 | 16.28 | 0 | 20268.6 | 20268.6 | 13512.4 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 13344.672 | [8 empty] | 0 | 0.6 | 0.6 | 0.4 | 0 | 8006.8032 | 8006.8032 | 5337.8688 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (Walk in closet 3)Sub-total: | [6 empty] | 124550.272 | [8 empty] | 0 | 65.72 | 65.72 | 25.37 | 0 | 61414.0032 | 61414.0032 | 63136.2688 | 45.71% |  | 0 | [15 empty] | 45.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (Walk in Center Table) | [23 empty] | 0%
| 3/4'' Marine Plywood | 20.34 | 22.374 | sq.m | 576 | 300 | 876 | 19599.624 | [8 empty] | 0 | 17.8992 | 17.8992 | 4.4748 | 0 | 15679.6992 | 15679.6992 | 3919.9248 | 80% |  | 0 | [15 empty] | 80% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 1.1 | 1.21 | sq.m | 330 | 165 | 495 | 598.95 | [8 empty] | 0 | 0.968 | 0.968 | 0.242 | 0 | 479.16 | 479.16 | 119.79 | 80% |  | 0 | [15 empty] | 80% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 1.5 | 1.65 | l.m | 220 | 110 | 330 | 544.5 | [8 empty] | 0 | 0 | 0 | 1.65 | 0 | 0 | 0 | 544.5 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Clear Glass Tempered | 1 | 1.1 | sq.m | 6600 | 3300 | 9900 | 10890 | [8 empty] | 0 | 0 | 0 | 1.1 | 0 | 0 | 0 | 10890 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 21.44 | 23.584 | sq.m | 555 | 275 | 830 | 19574.72 | [8 empty] | 0 | 7.0752 | 7.0752 | 16.5088 | 0 | 5872.416 | 5872.416 | 13702.304 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 6144.9353 | [8 empty] | 0 | 0.3 | 0.3 | 0.7 | 0 | 1843.4806 | 1843.4806 | 4301.4547 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (Walk in Center Table) Sub-total: | [6 empty] | 57352.7293 | [8 empty] | 0 | 26.2424 | 26.2424 | 24.6756 | 0 | 23874.7558 | 23874.7558 | 33477.9735 | 36.67% |  | 0 | [15 empty] | 36.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (lavatory sink T&B) | [23 empty] | 0%
| 3/4'' Marine Plywood | 9.2 | 10.12 | sq.m | 576 | 300 | 876 | 8865.12 | [8 empty] | 0 | 6.072 | 6.072 | 4.048 | 0 | 5319.072 | 5319.072 | 3546.048 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 1 | 1.1 | sq.m | 330 | 165 | 495 | 544.5 | [8 empty] | 0 | 0.66 | 0.66 | 0.44 | 0 | 326.7 | 326.7 | 217.8 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Mirror | 4 | 4.4 | sq.m | 1265 | 640 | 1905 | 8382 |  |  | 46.2 | [5 empty] | 0 | 0 | 0 | 4.4 | 0 | 0 | 0 | 8382 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer laminated | 10.2 | 11.22 | sq.m | 2640 | 880 | 3520 | 39494.4 |  |  | 18 | [5 empty] | 0 | 0 | 0 | 11.22 | 0 | 0 | 0 | 39494.4 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Quartz White sintered stone | 1.1 | 1.21 | sq.m | 6600 | 3300 | 9900 | 11979 | [8 empty] | 0 | 0 | 0 | 1.21 | 0 | 0 | 0 | 11979 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer Edge Laminate | 15 | 16.5 | l.m | 55 | 30 | 85 | 1402.5 |  |  | 19.26 | [5 empty] | 0 | 9.9 | 9.9 | 6.6 | 0 | 841.5 | 841.5 | 561 | 60% |  | 0 | [15 empty] | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 8480.1024 | [8 empty] | 0 | 0.3 | 0.3 | 0.7 | 0 | 2544.0307 | 2544.0307 | 5936.0717 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Master's Bedroom (lavatory sink T&B) Sub-total: | [6 empty] | 79147.6224 | [8 empty] | 0 | 16.932 | 16.932 | 28.618 | 0 | 9031.3027 | 9031.3027 | 70116.3197 | 30% |  | 0 | [15 empty] | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Memorabilia (Closet) | [23 empty] | 0%
| 3/4'' Marine Plywood | 24.36 | 26.796 | sq.m | 576 | 300 | 876 | 23473.296 | [8 empty] | 0 | 5.3592 | 5.3592 | 21.4368 | 0 | 4694.6592 | 4694.6592 | 18778.6368 | 20% |  | 0 | [15 empty] | 20% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 5.5 | 6.05 | sq.m | 330 | 165 | 495 | 2994.75 | [8 empty] | 0 | 1.21 | 1.21 | 4.84 | 0 | 598.95 | 598.95 | 2395.8 | 20% |  | 0 | [15 empty] | 20% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
| Warm Strip Lights | 7.81 | 8.591 | l.m | 220 | 110 | 330 | 2835.03 | [8 empty] | 0 | 1.7182 | 1.7182 | 6.8728 | 0 | 567.006 | 567.006 | 2268.024 | 20% |  | 0 | [15 empty] | 20% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
| Clear Glass Door | 3.9 | 4.29 | sq.m | 6600 | 3300 | 9900 | 42471 | [8 empty] | 0 | 0.858 | 0.858 | 3.432 | 0 | 8494.2 | 8494.2 | 33976.8 | 20% |  | 0 | [15 empty] | 20% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer laminated | 29.86 | 32.846 | sq.m | 2640 | 880 | 3520 | 115617.92 | [8 empty] | 0 | 6.5692 | 6.5692 | 26.2768 | 0 | 23123.584 | 23123.584 | 92494.336 | 20% |  | 0 | [15 empty] | 20% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
| Veneer Edge Laminate | 69.3 | 76.23 | l.m | 55 | 30 | 85 | 6479.55 | [8 empty] | 0 | 15.246 | 15.246 | 60.984 | 0 | 1295.91 | 1295.91 | 5183.64 | 20% |  | 0 | [15 empty] | 20% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 23264.5855 | [8 empty] | 0 | 0.2 | 0.2 | 0.8 | 0 | 4652.9171 | 4652.9171 | 18611.6684 | 20% |  | 0 | [15 empty] | 20% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
| Memorabilia (Closet) Sub-total: | [6 empty] | 217136.1315 | [6 empty] | 5082097.2 | 56700 | 0 | 31.1606 | 31.1606 | 124.6424 | 0 | 43427.2263 | 43427.2263 | 173708.9052 | 20% |  | 0 | [15 empty] | 20% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
| Roof Deck (Cabinet Detail 1) | [23 empty] | 0%
| 3/4'' Marine Plywood | 29.6 | 32.56 | sq.m | 576 | 300 | 876 | 28522.56 | [8 empty] | 0 | 32.56 | 32.56 | 0 | 0 | 28522.56 | 28522.56 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 2.1 | 2.31 | sq.m | 330 | 165 | 495 | 1143.45 | [8 empty] | 0 | 2.31 | 2.31 | 0 | 0 | 1143.45 | 1143.45 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| Quartz White sintered stone | 1.7 | 1.87 | sq.m | 6600 | 3300 | 9900 | 18513 | [8 empty] | 0 | 0 | 0 | 1.87 | 0 | 0 | 0 | 18513 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ducco Finish | 31.7 | 34.87 | sq.m | 555 | 275 | 830 | 28942.1 | [8 empty] | 0 | 17.435 | 17.435 | 17.435 | 0 | 14471.05 | 14471.05 | 14471.05 | 50% |  | 0 | [15 empty] | 50% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 9254.5332 | [5 empty] | 19.4 |  |  | 0 | 0.5 | 0.5 | 0.5 | 0 | 4627.2666 | 4627.2666 | 4627.2666 | 50% |  | 0 | [15 empty] | 50% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0%
| Roof Deck (Cabinet Detail 1) Sub-total: | [6 empty] | 86375.6432 | [5 empty] | 13.2 | 5082097.2 | 56700 | 0 | 52.805 | 52.805 | 19.805 | 0 | 48764.3266 | 48764.3266 | 37611.3166 | 60% |  | 0 | [15 empty] | 60% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0%
| Roof Deck (Cabinet Datail 2) | [12 empty] | 7.2 | [10 empty] | 0%
| 3/4'' Marine Plywood | 19.98 | 21.978 | sq.m | 576 | 300 | 876 | 19252.728 | [5 empty] | 23.88 |  |  | 0 | 21.978 | 21.978 | 0 | 0 | 19252.728 | 19252.728 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| 1/2'' Backing Marine plywood | 3.6 | 3.96 | sq.m | 330 | 165 | 495 | 1960.2 | [8 empty] | 0 | 3.96 | 3.96 | 0 | 0 | 1960.2 | 1960.2 | 0 | 100% |  | 0 | [15 empty] | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| Pvc Fluted Panels | 5 | 3.96 | sq.m | 880 | 450 | 1330 | 5266.8 |  | 1.1 | [6 empty] | 0 | 0 | 0 | 3.96 | 0 | 0 | 0 | 5266.8 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Quartz White sintered stone | 6.73 | 7.403 | sq.m | 6600 | 3300 | 9900 | 73289.7 | [8 empty] | 0 | 0 | 0 | 7.403 | 0 | 0 | 0 | 73289.7 | 0% |  | 0 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous and other Consumables |  | 1 | lot |  |  |  | 11972.3314 | [8 empty] | 0 | 0.4 | 0.4 | 0.6 | 0 | 4788.9325 | 4788.9325 | 7183.3988 | 40% |  | 0 | [15 empty] | 40% | 0% | 40% | 0% | 0% | 0% | 0% | 0% | 0%
| Roof Deck (Cabinet Detail 2) Sub-total: | [6 empty] | 111741.7594 | [6 empty] | 5082097.2 | 56700 | 0 | 26.338 | 26.338 | 11.963 | 0 | 26001.8605 | 26001.8605 | 85739.8988 | 48% |  | 0 | [15 empty] | 48% | 0% | 48% | 0% | 0% | 0% | 0% | 0% | 0%
| Third Floor Cabinet's Sub-total: | [6 empty] | 1204064.0797 | [8 empty] | 0 | 406.7233 | 406.7233 | 387.1807 | 0 | 430142.5762 | 430142.5762 | 773921.5034 | 39.04% |  | 0 | [15 empty] | 39.04% | 0% | 31.8% | 0% | 0% | 0% | 0% | 0% | 0%
| Cabinet's Sub-total: | [6 empty] | 2421974.5711 | [8 empty] | 0 | 907.0081 | 907.0081 | 926.766 | 0 | 996590.4975 | 996590.4975 | 1425384.0736 | 36.21% |  | 0 | [15 empty] | 36.21% | 0% | 12.03% | 0% | 0% | 0% | 0% | 0% | 0%
6.3
Unit 6&7 E.M Razon Commercial Building, San Pedro Camuning,
Mexico, Pampanga, Philippines 2021
09951119535 | clients@saikobuilders.com

## DOORS & WINDOW, PLUMBING, WOODE
Project name : | PROPOSED THREE STORY RESIDENCE
Location : | GRAND CENTENIAL HOMES KAWIT CAVITE
Date : | 2026-08-17
[17 empty] | QUANTITY | [7 empty] | AMOUNT | [7 empty] | ACCOMPLISHMENT | PREVIOUS ACCOMPLISHMENT
ITEM NO | Description | QUANTITY | UNIT | Material Cost Php/unit | Labor and Equipment Cost Php/unit | Total Cost Php/Unit | Total Amount Php | QUANTITY |  |  |  | AMOUNT |  |  |  | PERCENTAGE | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | BILLING | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8
| DOORS ( Door Jamb included) | [6 empty] | PREVIOUS | THIS DATE | TO DATE | BALANCE | PREVIOUS | THIS DATE | TO DATE | BALANCE | Accomplishment
D1 | 1.20X2.40 ( MAIN DOOR ) MAHOGANY WOOD PANEL DOOR WITH PIVOT HINGE MECHANISM | 1 | sets | 25300 | 13300 | 38600 | 38600 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 38600 | 0% | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
D2 | 1.26x2.40 (2ND FLR HALLWAY) MAHOGANY WOOD PANEL DOOR AND FIXED WINDOW WITH 2"X6" DOOR JAMB | 1 | sets | 25300 | 13300 | 38600 | 38600 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 38600 | 0% | [18 empty] | 0%
D3 | 0.80x2.40 (MASTER'S BEDROOM, BEDROOM 1,2,3,4, & ROOF DECK) MAHOGANY WOOD PANEL DOOR WITH 2"X6" DOOR JAMB | 6 | sets | FREE | FREE
D4 | 0.70x2.40 (OFFICE, T ANDB ,&POWDER ROOM) MAHOGANY WOOD PANEL DOOR WITH 2"X6" DOOR JAMB | 5 | sets | 23100 | 12130 | 35230 | 176150 | 0 | 2.5 | 2.5 | 2.5 | 0 | 88075 | 88075 | 88075 | 50% | [16 empty] | 50% |  | 50%
DK1 | Digital Door Knob | 1 | sets | 37400 | 19640 | 57040 | 57040 | 0 | 0.5 | 0.5 | 0.5 | 0 | 28520 | 28520 | 28520 | 50% | [16 empty] | 50% |  | 0%
DK2 | Door Knob | 12 | sets | 9130 | 4800 | 13930 | 167160 | 0 | 6 | 6 | 6 | 0 | 83580 | 83580 | 83580 | 50% | [16 empty] | 50% |  | 0%
D5 | 1.20x2.40 (KITCHEN AREA, 2ND AND 3RD FLR BALCONY) ALUMINUM FRAMED 6MM THK. ANNEALED GLASS DOOR | 3 | sets | 18220 | 9572.4 | 27792.4 | 83377.2 | 0 | 1.5 | 1.5 | 1.5 | 0 | 41688.6 | 41688.6 | 41688.6 | 50% | [16 empty] | 50% |  | 50%
SD1 | 3.20x2.40 (LIVING AND DINING AREA) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 3 | sets | 50100 | 26312 | 76412 | 229236 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 229236 | 0% | [16 empty] | 0% |  | 100%
SD2 | 2.65x2.40 (DINING AREA) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 1 | sets | 48700 | 25574 | 74274 | 74274 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 74274 | 0% | [16 empty] | 0% |  | 100%
SD3 | 2.00x2.40 (OFFICE ROOM) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED AND SWING GLASS DOOR | 1 | sets | 33300 | 17486 | 50786 | 50786 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 50786 | 0% | [16 empty] | 0% |  | 100%
SD4 | 1.80x2.40 (BEDROOM 1 AND 2) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 2 | sets | 27330 | 14348.6 | 41678.6 | 83357.2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 83357.2 | 0% | [16 empty] | 0% |  | 100%
SD5 | 2.80x2.80 (BEDROOM 4) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 1 | sets | 51480 | 27031.6 | 78511.6 | 78511.6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 78511.6 | 0% | [16 empty] | 0% |  | 100%
SD6 | 3.15x2.40 (WALK-IN CLOSET) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING MIRROR GLASS DOOR | 1 | sets | 47820 | 25109.4 | 72929.4 | 72929.4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 72929.4 | 0% | [16 empty] | 0% |  | 100%
SD7 | 3.00x2.40 (MASTER'S BEDROOM) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 1 | sets | 45540 | 23916.8 | 69456.8 | 69456.8 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 69456.8 | 0% | [16 empty] | 0% |  | 100%
SD8 | 2.27x2.40 (MEMORABILIA) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 1 | sets | 34160 | 17937.2 | 52097.2 | 52097.2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 52097.2 | 0% | [16 empty] | 0% |  | 100%
| Sub-Total For Doors | [5 empty] | 1271575.4 | 0 | 10.5 | 10.5 | 23.5 | 0 | 241863.6 | 241863.6 | 1029711.8 | 14.29% | [17 empty] | 0% | 64.29% | 0% | 0% | 0% | 0% | 0% | 0%
WINDOWS
W1 | 2.40X2.40 (FOYER) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW | 1 | sets | 24290 | 12761.8 | 37051.8 | 37051.8 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 37051.8 | 0% | [16 empty] | 0% |  | 100%
W2 | 2.00x2.40 (OFFICE ROOM) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW | 1 | sets | 21260 | 11169.2 | 32429.2 | 32429.2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 32429.2 | 0% | [16 empty] | 0% |  | 100%
W3 | 0.60x1.80 {BEDROOM 1,2,4 And Master's BEDROOM) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW WITH AWNING WINDOW | 5 | sets | 6380 | 3349.6 | 9729.6 | 48648 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 48648 | 0% | [16 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
W4 | 0.60x0.60 (BEDROOM 2 T AND B, MASTER'S T & B) ALUMINUM FRAMED 6MM THK. ANNEALED AWNING WINDOW | 2 | sets | 2750 | 1445 | 4195 | 8390 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 8390 | 0% | [16 empty] | 0% |  | 100%
W5 | 0.90x1.50(2ND FLR COMMON T AND B) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW | 1 | sets | 5720 | 3012.4 | 8732.4 | 8732.4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 8732.4 | 0% | [16 empty] | 0% |  | 100%
W6 | 1.80x1.50 (BEDROOM 3) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING WINDOW | 1 | sets | 13750 | 7225 | 20975 | 20975 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 20975 | 0% | [16 empty] | 0% |  | 100%
W7 | 1.00x1.80 (MASTER'S BEDROOM) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW | 1 | sets | 9350 | 4917 | 14267 | 14267 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 14267 | 0% | [16 empty] | 0% |  | 100%
W8 | 2.70x1.43 (MASTER'S TOILET AND BATH) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW | 1 | sets | 20020 | 10518.4 | 30538.4 | 30538.4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 30538.4 | 0% | [16 empty] | 0% |  | 100%
| Sub --Total For Window | [5 empty] | 201031.8 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 201031.8 | 0% | [17 empty] | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
SHOWER ENCLOSURE
SD9 | 2.82X2.40 (MASTER'S TOILET AND BATH SHOWER ENCLOSURE) 6MM THK TEMPERED GLASS | 1 | sets | 6600 | 3300 | 9900 | 9900 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 9900 | 0%
SD10 | 1.37x2.18 (BEDROOM 2 (T & B SHOWER ENCLOSURE) GOLD ALUMINUM FRAMED 6MM THK. FIXED AND SLIDING GLASS | 1 | sets | 6600 | 3300 | 9900 | 9900 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 9900 | 0%
M1 | 0.45x1.15 (BEDROOM 2 (T & B)) 6MM THK MIRROR GLASS | 1 | sets | 6600 | 3300 | 9900 | 9900 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 9900 | 0%
M2 | 1.47x1.22 (MASTER'S TOILET AND BATH) 6MM THK MIRROR GLASS | 1 | sets | 6600 | 3300 | 9900 | 9900 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 9900 | 0%
M3 | 1.00x1.30(WALK-IN CLOSET) 6MM THK MIRROR GLASS WITH STRIP LIGHT | 1 | sets | 6600 | 3300 | 9900 | 9900 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 9900 | 0%
M4 | 1.35x0.90 (BEDROOM 1) 6MM THK MIRROR GLASS | 1 | sets | 6600 | 3300 | 9900 | 9900 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 9900 | 0%
M5 | 1.60x0.90 (BEDROOM 3) 6MM THK MIRROR GLASS | 1 | sets | 6600 | 3300 | 9900 | 9900 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 9900 | 0%
M6 | 2.00x0.90 (BEDROOM 4) 6MM THK MIRROR GLASS | 1 | sets | 6600 | 3300 | 9900 | 9900 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 9900 | 0%
M7 | 0.80x2.70 (FOYER) 6MM THK MIRROR GLASS | 1 | sets | 6600 | 3300 | 9900 | 9900 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 9900 | 0%
| Sub-total for Shower Enclosure | [5 empty] | 89100 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 89100 | 0%
| Total for doors and window: | [5 empty] | 1561707.2 | 0 | 10.5 | 10.5 | 45.5 | 0 | 241863.6 | 241863.6 | 1319843.6 | 4.762% | [17 empty] | 0% | 54.76% | 0% | 0% | 0% | 0% | 0% | 0%
C | PLUMBING FIIXTURES
WC | Water Closet | 4 | sets | OSM | 1500 | 1500 | 6000 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 6000 | 0%
LS | Lavatory/Sink | 6 | sets | OSM | 3000 | 3000 | 18000 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 18000 | 0%
BT | Bathtub | 2 | sets | OSM | 4000 | 4000 | 8000 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 8000 | 0% | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
SS | Shower Set | 2 | sets | OSM | 2000 | 2000 | 4000 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4000 | 0%
B | Bidet | 4 | sets | OSM | 500 | 500 | 2000 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 2000 | 0%
FD | Floor Drain | 5 | sets | OSM | 500 | 500 | 2500 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 2500 | 0%
KS | Kitchen Sink | 2 | sets | OSM | 500 | 500 | 1000 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1000 | 0%
F | Faucet | 10 | sets | OSM | 1500 | 1500 | 15000 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 15000 | 0%
| Plumbing Fixtures Sub-Total: | [5 empty] | 56500 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 56500 | 0% | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Unit 6&7 E.M Razon Commercial Building, San Pedro Camuning,
Mexico, Pampanga, Philippines 2021
09951119535 | clients@saikobuilders.com

## ELECTRICAL
Project name : | PROPOSED THREE STORY RESIDENCE
Location : | GRAND CENTENIAL HOMES KAWIT CAVITE
Date : | 2026-08-17
[28 empty] | QUANTITY | [7 empty] | AMOUNT
ITEM NO | Description | QUANTITY | QUANTITY | UNIT | Material Cost Php/unit | Labor and Equipment Cost Php/unit | Total Cost Php/Unit | Total Amount Php | [10 empty] | QUANTITY |  |  |  | AMOUNT |  |  |  | PERCENTAGE | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8 | ACCOMPLISHMENT | PREVIOUS ACCOMPLISHMENT
D | ELECTRICAL WORKS | [17 empty] | PREVIOUS | THIS DATE | TO DATE | BALANCE | PREVIOUS | THIS DATE | TO DATE | BALANCE | Accomplishment | [16 empty] | BILLING | BILLING 1 | BILLING 2 | BILLING 3 | BILLING 4 | BILLING 5 | BILLING 6 | BILLING 7 | BILLING 8
Lighting Fixtures, Outlets and Switches
| Outlets | [8 empty] | 1.1 | QUANTITY
| Motor Outlets | 9 | 10 | pcs | 275 | 550 | 825 | 8250 |  | 0.08 | MISCELLANEOUS | [7 empty] | 0 | 4 | 4 | 6 | 0 | 3300 | 3300 | 4950 | 40% | [16 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Convinience Outlets | 64 | 71 | pcs | 275 | 550 | 825 | 58575 | [10 empty] | 0 | 28.4 | 28.4 | 42.6 | 0 | 23430 | 23430 | 35145 | 40% | [16 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Outlets Sub-total: | [6 empty] | 66825 | [10 empty] | 0 | 32.4 | 32.4 | 48.6 | 0 | 26730 | 26730 | 40095 | 40% | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Switches
| 1 gang | 15 | 17 | pcs | 176 | 550 | 726 | 12342 | [10 empty] | 0 | 5.95 | 5.95 | 11.05 | 0 | 4319.7 | 4319.7 | 8022.3 | 35% | [16 empty] | 35% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 2 gang | 11 | 13 | pcs | 297 | 550 | 847 | 11011 | [10 empty] | 0 | 4.55 | 4.55 | 8.45 | 0 | 3853.85 | 3853.85 | 7157.15 | 35% | [16 empty] | 35% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3 gang | 14 | 16 | pcs | 418 | 550 | 968 | 15488 | [10 empty] | 0 | 6.4 | 6.4 | 9.6 | 0 | 6195.2 | 6195.2 | 9292.8 | 40% | [16 empty] | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Switches Sub-total: | [6 empty] | 38841 | [10 empty] | 0 | 16.9 | 16.9 | 29.1 | 0 | 14368.75 | 14368.75 | 24472.25 | 36.67% | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Lighting Fixtures
| Pinlights | 94 | 104 | pcs | 440 | 550 | 990 | 102960 | [10 empty] | 0 | 20.8 | 20.8 | 83.2 | 0 | 20592 | 20592 | 82368 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Twin Pin Lights | 18 | 18 | pcs | 730 | 550 | 1280 | 23040 |  |  | For 387 sq.m residential (3-storey, almost luxury): | [7 empty] | 0 | 3.6 | 3.6 | 14.4 | 0 | 4608 | 4608 | 18432 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Strip Lights (3500K) | 120 | 132 | Im | 132 | 550 | 682 | 90024 | [10 empty] | 0 | 26.4 | 26.4 | 105.6 | 0 | 18004.8 | 18004.8 | 72019.2 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Round Center Lights |  | 5 | pcs | 1100 | 550 | 1650 | 8250 | [10 empty] | 0 | 1 | 1 | 4 | 0 | 1650 | 1650 | 6600 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Accent Lights |  | 3 | pcs | 1100 | 550 | 1650 | 4950 |  |  | 387 | sq.m | actual wires | [5 empty] | 0 | 0.6 | 0.6 | 2.4 | 0 | 990 | 990 | 3960 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Pendant Lights | 15 | 12 | pcs | 7700 | 550 | 8250 | 99000 |  |  | Lighting (2.0 mm²): ~2.5–3.5 lm per sqm | 1161 | 1098.02 | Good |  |  |  |  | 0 | 2.4 | 2.4 | 9.6 | 0 | 19800 | 19800 | 79200 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Chandelier |  | 1 | pcs | 140250 | 7700 | 147950 | 147950 |  |  | Convenience outlets (3.5 mm²): ~0.8–1.2 lm per sqm | 387 | 381.7 | Good |  |  |  |  | 0 | 0.2 | 0.2 | 0.8 | 0 | 29590 | 29590 | 118360 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Wall Lamps |  | 5 | pcs | 5500 | 550 | 6050 | 30250 |  |  | Higher loads / AC / kitchen (5.5 mm²): ~0.5–0.8 lm per sqm | 251.55 | 247.5 | Good |  |  |  |  | 0 | 1 | 1 | 4 | 0 | 6050 | 6050 | 24200 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Integrated fan light |  | 3 | pcs | 11000 | 550 | 11550 | 34650 | [10 empty] | 0 | 0.6 | 0.6 | 2.4 | 0 | 6930 | 6930 | 27720 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Magnetic Track light | 9.4 | 11 | l.m | 5500 | 550 | 6050 | 66550 | [10 empty] | 0 | 2.2 | 2.2 | 8.8 | 0 | 13310 | 13310 | 53240 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Lighting Fixtures Sub-total: | [6 empty] | 607624 | 0.05 | miscellaneous | [8 empty] | 0 | 58.8 | 58.8 | 235.2 | 0 | 121524.8 | 121524.8 | 486099.2 | 20% | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Wires
| OUTLETS | [12 empty] | STRIP LIGHTS
| 3.5 mm | 347 | 381.7 | l.m | 41.36 | 165 | 206.36 | 78767.612 | 1.1 | QUANTITY |  |  | 8.6 | 34.4 |  |  |  |  | 0 | 76.34 | 76.34 | 305.36 | 0 | 15753.5224 | 15753.5224 | 63014.0896 | 20% | [16 empty] | 20% | 50% | 30% | 0 | 0 | 0 | 0 | 0 | 0
| 5.5 mm | 225 | 247.5 | l.m | 58.52 | 165 | 223.52 | 55321.2 | [5 empty] | 9.6 |  |  |  |  | 0 | 49.5 | 49.5 | 198 | 0 | 11064.24 | 11064.24 | 44256.96 | 20% | [16 empty] | 20% | 40% | 40%
| LIGHTING | [12 empty] | 25.9
| 2.0mm | 998.2 | 1098.02 | l.m | 38.5 | 165 | 203.5 | 223447.07 | 1.1 |  |  |  |  | 68.2 |  |  |  |  | 0 | 329.406 | 329.406 | 768.614 | 0 | 67034.121 | 67034.121 | 156412.949 | 30% | [16 empty] | 30% | 20% | 20%
| Miscellaneuos and Other accessories |  | 1 | lot |  |  |  | 17876.7941 | [10 empty] | 0 | 0.15 | 0.15 | 0.85 | 0 | 2681.5191 | 2681.5191 | 15195.275 | 15% | [16 empty] | 15% | 49% | 30%
| Wires Sub-total: | [6 empty] | 375412.6761 | [10 empty] | 0 | 455.396 | 455.396 | 1272.824 | 0 | 96533.4025 | 96533.4025 | 278879.2736 | 21.25% | [17 empty] | 39.75% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
Panel Board
Feeder Line
| 80mm | 30 | 33 | l.m | 661 | 350 | 1011 | 33363 | [10 empty] | 0 | 6.6 | 6.6 | 26.4 | 0 | 6672.6 | 6672.6 | 26690.4 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 14mm | 15 | 16.5 | l.m | 132 | 275 | 407 | 6715.5 | [10 empty] | 0 | 3.3 | 3.3 | 13.2 | 0 | 1343.1 | 1343.1 | 5372.4 | 20% | [16 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Circuit Breaker's (schneider)
| PANEL BOARD 26BRS MAIN: EZC 200A, 2P(MCCB) |  | 1 | set's | 35200 | 19360 | 54560 | 54560 | [10 empty] | 0 | 0.1 | 0.1 | 0.9 | 0 | 5456 | 5456 | 49104 | 10% | [16 empty] | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IC60N 15A, 2P(MCB)
IC60N 20A, 2P(MCB)
IC60N 30A, 2P(MCB)
IC60N 40A, 2P(MCB)
| W/GROUNDING BUSBAR | [7 empty] | 0.2 | miscellaneous
27340
| Conduits | 45 | 49.5 | l.m | 154 | 46.2 | 200.2 | 9909.9 | [5 empty] | #REF! |  |  |  |  | 0 | 0 | 0 | 49.5 | 0 | 0 | 0 | 9909.9 | 0% | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Entrance Cap |  | 1 | pcs | 126.5 | 37.95 | 164.45 | 164.45 | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 164.45 | 0% | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Miscellaneous |  | 1 | lot |  |  |  | 20942.57 | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 20942.57 | 0% | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EMT Connector
Steel Clamp
Threaded Elbow 90 degree
Rubber Tape
Electrical Tape
Bushing
Locknut
EMT Coupling
| Panel Board Sub-total: | [6 empty] | 125655.42 | [10 empty] | 0 | 10 | 10 | 92 | 0 | 13471.7 | 13471.7 | 112183.72 | 8.333% | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| ELECTRICAL WORKS SUB-TOTAL: | [6 empty] | 1214358.0961 | [6 empty] | 1 | 2 | 3 |  | 0 | 573.496 | 573.496 | 1677.724 | 0 | 272628.6525 | 272628.6525 | 941729.4436 | 25.25% | [17 empty] | 7.95% | 6% | 0% | 0% | 0% | 0% | 0% | 0%
[14 empty] | Pinlights | 18 | 40 | 35 | 93
[14 empty] | Strip Lights |  |  |  | 0
[14 empty] | Pendant Lights | 3 | 7 | 4 | 14
Unit 6&7 E.M Razon Commercial Building, San Pedro Camuning,
Mexico, Pampanga, Philippines 2021
09951119535 | clients@saikobuilders.com

## Material and Labor Cost (hidden)
SUPPLIER | Descriptions | Material | Material Markup | Labor | Labor Markup | M | L
| Gypsum Board | 200 | 250 | 300 | 350 | 30 | 20
| CARRYING channel | 115 | 126.5 | 57.5 | 70 |  | 6.75
| Metal Furring | 115 | 126.5 | 57.5 | 70 |  | 6.75
| Hanger clips | 25 | 30 | 15 | 20 | 2.5 | 3.5 | 1.1 | Material
| W clips | 5 | 10 | 15 | 20 | 4.5 | 3.5 | 1.1 | Labor
| Wall Angle | 100 | 110 | 50 | 60 |  | 5 | 0.5 | Cabinets labor
| Paint flat finish | 200 | 250 | 300 | 350 | 30 | 20
| PVC CEILING PANEL | 200 | 250 | 300 | 350 | 30 | 20 | 0.4 | glass labor
| H CLIP ceiling panel | 100 | 110 | 15 | 20 |  | 3.5
| pvc ceiling panel edging | 100 | 110 | 15 | 20 |  | 3.5
| FICEM BOARD | 200 | 250 | 300 | 350 | 30 | 20
2.98
| UV Board Marble | 500 | 555 | 250 | 300 | 5 | 25
| 3/4'' Marine Plyboard | 520 | 576 | 260 | 300 | 4 | 14 |  |  | 3/4'' Marine Plyboard | 1530 | 514
| Pvc Fluted Panels | 800 | 880 | 400 | 450 |  | 10 |  |  | 1/2'' Backing Marine plyboard | 820 | 276
| 1/2'' Backing Marine plyboard | 300 | 330 | 150 | 165
| Warm Strip Lights | 200 | 220 | 100 | 110
| Paint Finish | 500 | 555 | 250 | 275 | 5
| Ducco Finish | 500 | 555 | 250 | 275 | 5
| Quartz White sintered stone | 6000 | 6600 | 3000 | 3300
| Veneer laminated | 2400 | 2640 | 792 | 880 |  | 8.8
| PVC Board | 680 | 748 | 340 | 380 |  | 6
| 1''x1''x2.0mm Tubular Steel | 63.8 | 70.18 | 31.9 | 35.09
| Coated Powder (Black) | 250 | 275 | 125 | 140 |  | 2.5
| Veneer Edge Laminate | 50 | 55 | 25 | 30 |  | 2.5
| Stainless Hanging Rod | 300 | 330 | 150 | 165
| Reflective Mirror | 1150 | 1265 | 575 | 640 |  | 7.5
| 2''x1''x2.0mm Tubular Steel | 63.8 | 70.18 | 31.9 | 35.09
| wood slatted Door | 500 | 550 | 250 | 275
| Clear Glass Door Gold framing | 6000 | 6600 | 3000 | 3300
Floor Finish (Interior)
Ground Floor
HALLWAY, LIVING, DINING TO KITCHEN AREA
| WHITE 600X600 mm MARBLE TILES HIGH GLOSS FINISH | 1200 | 1320 | 300 | 350 |  | 20
Office room
| WHITE 600X600 mm MARBLE TILES HIGH GLOSS FINISH | 1200 | 1320 | 300 | 350 |  | 20
Powder room
| 300X300 mm WHITE MARBLE TILES NON SKID | 800 | 880 | 300 | 350 |  | 20
0
| Second Floor |  | 0
| Hallway |  | 0
| SPC WOOD | 250 | 300 | 300 | 350 | 25 | 20
0
| Bedroom 1 |  | 0
| SPC WOOD | 250 | 300 | 300 | 350 | 25 | 20
0
| Bedrorm 2 |  | 0
| SPC WOOD | 250 | 300 | 300 | 350 | 25 | 20
0
| Bedroom 3 |  | 0
| SPC WOOD | 250 | 300 | 300 | 350 | 25 | 20
0
| Bedroom 4 |  | 0
| SPC WOOD | 250 | 300 | 300 | 350 | 25 | 20
0
| Toilet and Bath bedrrom 2 |  | 0
| 300X300 mm LIGHT GRAY TILES MARBLE LOOK IN NON- SKID FINISH | 800 | 880 | 300 | 350 |  | 20
0
| Toilet and Bath bedrrom |  | 0
| 600x600mm White Tiles In Marble Look Non Skid | 850 | 940 | 300 | 350 | 5 | 20
0
| Balcony |  | 0
| 600x600mm Non Skid Gray Tiles | 750 | 830 | 300 | 350 | 5 | 20
0
0
| Third Floor |  | 0
| Hallway |  | 0
| SPC WOOD | 250 | 300 | 300 | 350 | 25 | 20
0
| Walk in Closet |  | 0
| SPC WOOD | 250 | 300 | 300 | 350 | 25 | 20
0
| Master's Bedroom |  | 0
| SPC WOOD | 250 | 300 | 300 | 350 | 25 | 20
0
| Master's T&B |  | 0
| 300X600mm Gray Marble Tiles in Non Skid Finish | 860 | 950 | 300 | 350 | 4 | 20
0
| Memorabilia |  | 0
| 300x300mm Light Gray Marbles Tiles | 800 | 880 | 300 | 350 |  | 20
0
| Viewdeck |  | 0
| 600x600mm Non Skid Gray Tiles | 750 | 830 | 300 | 350 | 5 | 20
0
| Balcony |  | 0
| 600x600mm Non Skid Gray Tiles | 750 | 830 | 300 | 350 | 5 | 20
0

## MATERIAL AND LABOR COST FOR WAL (hidden)
SUPPLIER | Description | material | material mark up | labor | labor mark up | m | L
Wall Finish
| Ground Floor ( Interior ) | [6 empty] | 1.1 | Material
FOYER, LIVING, DINING AND KITCHEN
| White Mouldings | 500 | 550 | 300 | 350 |  | 20 | 1.1 | Labor
| Hidden Door PU Stone Finish Light Beige | 1950 | 2150 | 1075 | 1200 | 5 | 17.5
| White Fluted | 800 | 880 | 300 | 350 |  | 20
| Laminated Synthetic Marble Finish | 3000 | 3300 | 1500 | 1650
| Back Splash Quartz/ White Sintered Stone Terazzo look Finish | 6000 | 6600 | 3000 | 3300
| Semi Gloss | 300 | 350 | 300 | 350 | 20 | 20
| Wood Laminated Finish | 750 | 825 | 300 | 350 |  | 20
| Beveled Clear Mirror | 1250 | 1375 | 625 | 700 |  | 12.5
OFFICE
| Biege Textured Wallpaper Finish | 750 | 825 | 300 | 350 |  | 20
| PU Stone Textured Light Biege Finish | 1950 | 2150 | 1075 | 1200 | 5 | 17.5
| 18 mm THK MDF Plywood Wall Cladding in Wood Finish w/ warm strip light | 1250 | 1375 | 625 | 700 |  | 12.5
| Semi Gloss Off White | 300 | 350 | 300 | 350 | 20 | 20
| 60X120 Gray Marble Tiles In High Gloss Finish | 500 | 550 | 300 | 350 |  | 20
Ground Floor ( Exterior )
| Exposed Aggregate Contcrete Cladding | 300 | 350 | 300 | 350 | 20 | 20
| Flashing ( Dark Gray ) | 500 | 550 | 300 | 350 |  | 20
| Wall Piaint Finish ( Off White ) | 300 | 350 | 300 | 350 | 20 | 20
| Natural Limestone Tiles Texture Running Ashlar Pattern | 850 | 950 | 300 | 350 | 15 | 20
| Wall Paint Finish ( Dark Gray ) | 300 | 350 | 300 | 350 | 20 | 20
Second Floor ( Interior )
BEDROOM 1
| Wall in Light Biege Semi-Gloss Painted Finish | 300 | 350 | 300 | 350 | 20 | 20
| Wall in Light Biege Semi-Gloss Painted Finish with mouldings | 500 | 550 | 300 | 350 |  | 20
BEDROOM 2 & T&B
| Wall in off Light semi gloss Painted Finish | 300 | 350 | 300 | 350 | 20 | 20
| Wall in Wood in Fluted Panel | 1000 | 1100 | 300 | 330
| Headboard in light brown leatherette | 300 | 350 | 300 | 350 | 20 | 20
| 30x60 Gray Tiles Marble look in High Gloss Finish | 860 | 950 | 300 | 350 | 4 | 20
| Mosaic Tiles Light Green Finish | 700 | 770 | 300 | 350 |  | 20
| Clear Mirror With Warm Light | 1300 | 1450 | 300 | 350 | 20 | 20
BEDROOM 3
| Wall off White in Semi Gloss Painted Finish | 300 | 350 | 300 | 350 | 20 | 20
| Wall Cladding in Fluted white Painted Finish | 800 | 880 | 300 | 330
| Headboard | 300 | 330 |  | 0
| Mouldings | 500 | 550 | 300 | 330
BEDROOM 4
| Stucco Cement Finish | 300 | 350 | 300 | 350 | 20 | 20
| Headboard | 300 | 330 | 300 | 350 |  | 20
| Mouldings | 500 | 550 | 300 | 330
HALLWAY
| Wall in Semi Gloss off White | 300 | 350 | 300 | 350 | 20 | 20
T&B
| White Mosaic Tiles In Semi Gloss Finish | 700 | 770 | 300 | 350 |  | 20
| 60x60 White Tiles In Marbles in Semi Gloss Finish | 580 | 650 | 300 | 350 | 12 | 20
| Texturia Interior Film in Wood Finish or Wood Tiles | 1200 | 1320 | 600 | 700 |  | 40
| Gray Quartz or Synthetic Counter Top | 6000 | 6600 | 3000 | 3300
Second Floor ( Exterior )
BALCONY
| Exposed Aggregate Contcrete Cladding | 300 | 350 | 300 | 350 | 20 | 20
| WPC Fluted Panel | 870 | 960 | 300 | 350 | 3 | 20
| Wall Piaint Finish ( Off White ) | 300 | 350 | 300 | 350 | 20 | 20
| Flashing ( Dark Gray ) | 500 | 550 | 300 | 350 |  | 20
| Natural Limestone Tiles Texture Running Ashlar Pattern | 850 | 950 | 300 | 350 | 15 | 20
Third Floor ( Interior )
WALK IN CLOSET
| White Semi Gloss | 300 | 350 | 300 | 350 | 20 | 20
MASTER'S BEDROOM
| Wall in White Textured Wall Finish | 300 | 350 | 300 | 350 | 20 | 20
| Wall in Wood Fluted Panel Finish | 1000 | 1100 | 300 | 330
MASTER'S T&B
| 30x60 Marbles Tiles in High Gloss Finish | 400 | 450 | 300 | 350 | 10 | 20
| 30x60 Light Biege Tiles in High Gloss Finish | 300 | 330 | 300 | 350 |  | 20
MEMORABILIA
| Wall Cladding in Wood Laminated Finish | 1000 | 1100 | 300 | 350 |  | 20
| Wall in Light Biege Semi- Gloss Painted Finish | 300 | 350 | 300 | 350 | 20 | 20
HALLWAY
| Wall in Semi Gloss off White Painted Finish | 300 | 350 | 300 | 350 | 20 | 20
| Wall in Light Biege Semi- Gloss Painted Finish | 300 | 330 | 300 | 350 |  | 20
Third Floor ( Exterior )
BALCONY
| Wall Paint Finish ( Off White ) | 300 | 350 | 300 | 350 | 20 | 20
| Natural Limestone Tiles Texture Running Ashlar Pattern | 850 | 950 | 300 | 350 | 15 | 20
| conrete cladding with groove lines | 300 | 350 | 300 | 350 | 20 | 20
STAIR
| Wall Cladding White Fluted in Ducco Painted Finish | 500 | 550 | 300 | 350 |  | 20
| Semi Gloss Off White | 300 | 350 | 300 | 350 | 20 | 20
| Wall Piaint Finish ( Dark Gray ) | 300 | 350 | 300 | 350 | 20 | 20
| Glass Railings stair | 5700 | 6300 | 1140 | 1260 | 30 | 6
| Glass Railings 2nd floor | 5700 | 6300 | 1140 | 1260 | 30 | 6
| Glass Railings 3rd floor | 5700 | 6300 | 1140 | 1260 | 30 | 6
| Beveled Clear Mirror | 1250 | 1375 | 625 | 700 |  | 12.5

## Materials labor doors and windo (hidden)
SUPPLIER | Description | Material Cost Php/unit | MATERIAL MARK UP | LABOR | LABOR MARK UP | M | L |  | DOOR
| DOORS | [6 empty] | 1.1 | MATERIALS
| 1.20X2.40 ( MAIN DOOR ) MAHOGANY WOOD PANEL DOOR WITH PIVOT HINGE MECHANISM | 23000 | 25300 | 12650 | 13300 |  | 17.5 | 1.05 | LABOR
| 1.26x2.40 (2ND FLR HALLWAY) MAHOGANY WOOD PANEL DOOR AND FIXED WINDOW WITH 2"X6" DOOR JAMB | 23000 | 25300 | 12650 | 13300 |  | 17.5 | 0.5 | LABOR
| 0.80x2.40 (MASTER'S BEDROOM, BEDROOM 1,2,3,4, & ROOF DECK) MAHOGANY WOOD PANEL DOOR WITH 2"X6" DOOR JAMB | 21000 | 23100 | 11550 | 12130 |  | 2.5 |  | WINDOW
| 0.70x2.40 (OFFICE, T ANDB ,&POWDER ROOM) MAHOGANY WOOD PANEL DOOR WITH 2"X6" DOOR JAMB | 21000 | 23100 | 11550 | 12130 |  | 2.5 | 1.1 | MATERIALS
| Digital Door Knob | 34000 | 37400 | 18700 | 19640 |  | 5
| Door Knob | 8300 | 9130 | 4565 | 4800 |  | 6.75
| 1.20x2.40 (KITCHEN AREA, 2ND AND 3RD FLR BALCONY) ALUMINUM FRAMED 6MM THK. ANNEALED GLASS DOOR | 16560 | 18220 | 9110 | 9572.4 | 4 | 6.9 | 1.05 | LABOR
| 3.20x2.40 (LIVING AND DINING AREA) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 45540 | 50100 | 25050 | 26312 | 6 | 9.5 | 0.5 | LABOR
| 2.65x2.40 (DINING AREA) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 44250 | 48700 | 24350 | 25574 | 25 | 6.5
| 2.00x2.40 (OFFICE ROOM) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED AND SWING GLASS DOOR | 30268 | 33300 | 16650 | 17486 | 5.2 | 3.5 |  | shower
| 1.80x2.40 (BEDROOM 1 AND 2) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 24840 | 27330 | 13665 | 14348.6 | 6 | 0.35 | 1.1 | materials
| 2.80x2.80 (BEDROOM 4) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 46800 | 51480 | 25740 | 27031.6 |  | 4.6 | 1.05 | labor
| 3.15x2.40 (WALK-IN CLOSET) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING MIRROR GLASS DOOR | 43470 | 47820 | 23910 | 25109.4 | 3 | 3.9 | 0.5 | labor
| 3.00x2.40 (MASTER'S BEDROOM) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 41400 | 45540 | 22770 | 23916.8 |  | 8.3
| 2.27x2.40 (MEMORABILIA) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING GLASS DOOR | 31050 | 34160 | 17080 | 17937.2 | 5 | 3.2
WINDOWS
| 2.40X2.40 (FOYER) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW | 22080 | 24290 | 12145 | 12761.8 | 2 | 9.55
| 2.00x2.40 (OFFICE ROOM) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW | 19320 | 21260 | 10630 | 11169.2 | 8 | 7.7
| 0.60x1.80 {BEDROOM 1,2,4 And Master's BEDROOM) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW WITH AWNING WINDOW | 5800 | 6380 | 3190 | 3349.6 |  | 0.1
| 0.60x0.60 (BEDROOM 2 T AND B, MASTER'S T & B) ALUMINUM FRAMED 6MM THK. ANNEALED AWNING WINDOW | 2500 | 2750 | 1375 | 1445 |  | 1.25
| 0.90x1.50(2ND FLR COMMON T AND B) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW | 5200 | 5720 | 2860 | 3012.4 |  | 9.4
| 1.80x1.50 (BEDROOM 3) ALUMINUM FRAMED 6MM THK. ANNEALED SLIDING WINDOW | 12500 | 13750 | 6875 | 7225 |  | 6.25
| 1.00x1.80 (MASTER'S BEDROOM) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW | 8500 | 9350 | 4675 | 4917 |  | 8.25
| 2.70x1.43 (MASTER'S TOILET AND BATH) ALUMINUM FRAMED 6MM THK. ANNEALED FIXED WINDOW | 18200 | 20020 | 10010 | 10518.4 |  | 7.9
|  |  | 0 |  | 0
| 2.82X2.40 (MASTER'S TOILET AND BATH SHOWER ENCLOSURE) 6MM THK TEMPERED GLASS | 6000 | 6600 | 3300 | 3300
| 1.37x2.18 (BEDROOM 2 (T & B SHOWER ENCLOSURE) GOLD ALUMINUM FRAMED 6MM THK. FIXED AND SLIDING GLASS | 6000 | 6600 | 3300 | 3300
| 0.45x1.15 (BEDROOM 2 (T & B)) 6MM THK MIRROR GLASS | 6000 | 6600 | 3300 | 3300
| 1.47x1.22 (MASTER'S TOILET AND BATH) 6MM THK MIRROR GLASS | 6000 | 6600 | 3300 | 3300
| 1.00x1.30(WALK-IN CLOSET) 6MM THK MIRROR GLASS WITH STRIP LIGHT | 6000 | 6600 | 3300 | 3300
| 1.35x0.90 (BEDROOM 1) 6MM THK MIRROR GLASS | 6000 | 6600 | 3300 | 3300
| 1.60x0.90 (BEDROOM 3) 6MM THK MIRROR GLASS | 6000 | 6600 | 3300 | 3300
| 2.00x0.90 (BEDROOM 4) 6MM THK MIRROR GLASS | 6000 | 6600 | 3300 | 3300
| 0.80x2.70 (FOYER) 6MM THK MIRROR GLASS | 6000 | 6600 | 3300 | 3300

## electrical labor and materials (hidden)
[8 empty] | 1.1 | material
[8 empty] | 1.1 | labor
SUPPLIER | Descriptions | Material | Material Markup | Labor | Labor Markup | M | L
ELECTRICAL WORKS
Lighting Fixtures, Outlets and Switches
Outlets
| Motor Outlets | 250 | 275 | 500 | 550
| Convinience Outlets | 250 | 275 | 500 | 550
Switches
| 1 gang | 160 | 176 | 500 | 550
| 2 gang | 270 | 297 | 500 | 550
| 3 gang | 380 | 418 | 500 | 550
| Twin Pin Lights | 660 | 730 | 500 | 550 | 4
| Pinlights | 400 | 440 | 500 | 550
| Strip Lights | 120 | 132 | 500 | 550
| round center lights | 1000 | 1100 | 500 | 550
| accent lights | 1000 | 1100 | 500 | 550
| Pendant Lights | 7000 | 7700 | 500 | 550
| Chandelier | 127500 | 140250 | 7000 | 7700
| Wall Lamps | 5000 | 5500 | 500 | 550
| Integrated fan light | 10000 | 11000 | 500 | 550
| Magnetic Track light | 5000 | 5500 | 500 | 550
Wires
OUTLETS
| 3.5 mm | 37.6 | 41.36 | 150 | 165
| 5.5 mm | 53.2 | 58.52 | 150 | 165
LIGHTING
| 3.5mm | 35 | 38.5 | 150 | 165
| MCB ( 200AT) Schneider | 15000 | 16500 | 4950 | 5445
| 15 AT | 400 | 440 | 132 | 145.2
| 20 AT | 400 | 440 | 132 | 145.2
| 30 AT | 500 | 550 | 165 | 181.5
| 40 AT | 500 | 550 | 165 | 181.5
| Panel Box |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
| Conduits | 140 | 154 | 46.2 | 50.82
| Entrance Cap | 115 | 126.5 | 37.95 | 41.745
| 80mm | 600 | 661 | 300 | 350 | 1 | 20
| 14mm | 120 | 132 | 250 | 275
| PANEL BOARD 26BRS MAIN: EZC 200A, 2P(MCCB) | 32000 | 35200 | 17600 | 19360
|  |  | 0 |  | 0
| IC60N 15A, 2P(MCB) |  | 0 |  | 0
| IC60N 20A, 2P(MCB) |  | 0 |  | 0
| IC60N 30A, 2P(MCB) |  | 0 |  | 0
| IC60N 40A, 2P(MCB) |  | 0 |  | 0
W/GROUNDING BUSBAR